## Instructions
Sheet | Instruction for Use
Project Plan_GANTT | Use this sheet first. Milestones mark major actions or events where there is a significant change or stage in development. Brainstorm the milestones for your project. Next, develop the high level tasks that go with each of your milestones. Fill in the dates and owners for milestones and tasks. Then highlight the cells to the right that show the timeframe these milestones and tasks are expected to take. This becomes your baseline project plan. Use the highlighting colors, as shown in the legend, to show current status as your project progresses. The formulas in the milestone dates (Min and Max) automatically calculate dates based upon the tasks beneath them. Be sure to change the formula if you add or eliminate tasks for your specific milestones. Also you can add/delete tasks here, but make sure to add/delete them to the RAIL as well to ensure they carry over. It is unnecessary to have every task from the RAIL on the GANTT. Be sure to keep your details in the RAIL and keep the GANTT clean and high-level if you can. General advice is to only put tasks on the GANTT which you want to show to the leadership team or other external audiences. Very detailed tasks can remain on the RAIL only.
Rail | This tool is used during team meetings to track more detailed tasks that are required to deliver the milestones. DO NOT feel the need to replicate what you have in the RAIL in the Project Plan_GANTT. The purpose of this sheet is to track, at a more detailed level, status during each team meeting. It also tracks who attends the team meetings and can help people who miss a meeting to quickly catch up. Store it in a shared digital folder such as Micrsoft Teams so that everyone can collaborate. As tasks are added or deleted, you can add them here. Remember to update the date of the latest project team meeting (top left) and the attendees for each team meeting (top - from middle to right of spreadsheet). Add meeting dates as your project progresses in the columns to the right. You do NOT Have to update each task for each team meeting. Only update those tasks which your team discusses. As a project manager and core team member, it is a good idea to look at the tasks (actions) before the meeting so that you focus on the right tasks for that meeting. Although you can start with the GANTT and RAIL aligned, as you progress, do not feel the need to keep these two equal. The GANTT is for the leadership team and others outside your project team. The RAIL is for your core team. Do not change cells which are shaded as they flow from the GANTT to the RAIL.
Dates | Note, in the RAIL and in the GANTT, each column represents one week. If you change the initial week date, the remaining cells will automatically calculate. As an example, changing cell E4 on the GANTT will then enable all columns past E (F, G…) to automatically calcluate. You will need to update (or delete) row 3 to keep the quarters aligned with your weeks. The same is true for cell K4 in the RAIL. Enter the first date of your team's meeting here. The spreadsheet will ensure all other dates automatically progress one week at a time.

## Project Plan_Gantt
Project Plan | Legend | Completed | On Track | Behind | Risk | Baseline - Plan
Project Name
|  |  |  | Q4'22 | [15 empty] | Q1'23
Milestones and Tasks & Week Starting | Start Date | End Date | Owner | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27
Workstream 1 | 2022-09-08 | 2023-04-01 | Owner 1
Cluster one - Freeze the plan | 2022-09-08 | 2022-09-29 | Owner 1
Cluster two - freeze the plan | 2022-09-29 | 2022-10-04 | Owner 1
Cluster three - freeze the plan | 2022-10-04 | 2022-10-11 | Owner 1
Task4 | 2022-10-11 | 2022-10-18 | Owner 1
Task5 | 2022-10-18 | 2022-10-25 | Owner 1
Task6 | 2022-10-25 | 2022-11-01 | Owner 1
Task7 | 2022-11-01 | 2022-12-01 | Owner 1
Task8 | 2022-12-01 | 2022-12-31 | Owner 1
Task9 | 2023-01-01 | 2023-01-31 | Owner 1
Task10 | 2023-01-01 | 2023-04-01 | Owner 1
Workstream 2 | 2022-09-07 | 2022-12-02 | Owner 2
Task1 | 2022-09-07 | 2022-09-21 | Owner 2
Task2 | 2022-09-21 | 2022-10-05 | Owner 2
Task3 | 2022-10-05 | 2022-10-12 | Owner 2
Task4 | 2022-10-12 | 2022-10-26 | Owner 2
Task5 | 2022-10-26 | 2022-11-02 | Owner 2
Task6 | 2022-11-02 | 2022-12-02 | Owner 2
Milestone 3 | 2022-09-15 | 2022-12-12 | Owner 3
Task1 | 2022-09-15 | 2022-09-29 | Owner 3
Task2 | 2022-09-29 | 2022-10-13 | Owner 3
Task3 | 2022-10-13 | 2022-10-27 | Owner 3
Task4 | 2022-10-27 | 2022-11-10 | Owner 3
Task5 | 2022-11-10 | 2022-11-24 | Owner 3
Task6 | 2022-10-13 | 2022-12-12 | Owner 3
Milestone 4 | 2022-09-06 | 2023-03-01 | Owner 4
Task1 | 2022-09-06 | 2022-09-30 | Owner 4
Task2 | 2022-09-15 | 2022-09-30 | Owner 4
Task3 | 2022-09-14 | 2022-09-21 | Owner 4
Task4 | 2022-09-21 | 2022-10-10 | Owner 4
Task5 | 2022-10-10 | 2022-10-15 | Owner 4
Task6 | 2022-09-14 | 2022-09-21 | Owner 4
Task7 | 2022-10-15 | 2022-10-30 | Owner 4
Task8 | 2022-10-15 | 2022-12-01 | Owner 4
Task9 | 2022-12-01 | 2022-12-30 | Owner 4
Task10 | 2023-01-01 | 2023-01-15 | Owner 4
Task11 | 2022-01-01 | 2023-03-01 | Owner 4
Milestone 5 | 2022-09-08 | 2022-12-17 | Owner 5
Task1 | 2022-09-08 | 2022-09-22 | Owner 5
Task2 | 2022-09-22 | 2022-10-06 | Owner 5
Task3 | 2022-10-06 | 2022-10-13 | Owner 5
Task4 | 2022-10-13 | 2022-10-20 | Owner 5
Task5 | 2022-10-20 | 2022-11-10 | Owner 5
Task6 | 2022-11-10 | 2022-11-17 | Owner 5
Task7 | 2022-11-17 | 2022-12-17 | Owner 5
Formulas:
Risk = 7+[Behind]
Baseline - Plan = 7+[Risk]
Legend = MIN([Legend, row below]:B15)
Legend = [Completed, row above]
Completed = MAX([Completed, row below]:C15)
Completed = 21+[Legend]

## RAIL
Rolling Action Item List and Tracking Status | [9 empty] | Meeting Attendees and Meeting dates (starting in cell M4) | Tracy, Susan | Names | Names | Names | Names
Initiative Name | Initiative |  | Status Legend
Recent Core Team Review | Project Name | Project Name |  | Not Started | In Progress | On Hold | Cancelled | Completed
Category | Item# | Action | Owner | Other Team members | Overall Status (enter status to update color) | Start Date | Target Complete Date | Tracking behind? | Actual Complete Date | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17
Workstream 1 | 1.1 | Cluster one - Freeze the plan | Owner 1 |  | Not Started | 2022-09-08 | 2022-09-29
Workstream 1 | 1.2 | Cluster two - freeze the plan | Owner 1 |  | Not Started | 2022-09-29 | 2022-10-04
Workstream 1 | 1.3 | Cluster three - freeze the plan | Owner 1 |  | Not Started | 2022-10-04 | 2022-10-11
Workstream 1 | 1.4 | Task4 | Owner 1 |  | Not Started | 2022-10-11 | 2022-10-18
Workstream 1 | 1.5 | Task5 | Owner 1 |  | Not Started | 2022-10-18 | 2022-10-25
Workstream 1 | 1.6 | Task6 | Owner 1 |  | Not Started | 2022-10-25 | 2022-11-01
Workstream 1 | 1.7 | Task7 | Owner 1 |  | Not Started | 2022-11-01 | 2022-12-01
Workstream 1 | 1.8 | Task8 | Owner 1 |  | Not Started | 2022-12-01 | 2022-12-31
Workstream 1 | 1.9 | Task9 | Owner 1 |  | Not Started | 2023-01-01 | 2023-01-31
Workstream 1 | 1.10 | Task10 | Owner 1 |  | Not Started | 2023-01-01 | 2023-04-01
Workstream 2 | 2.1 | Task1 | Owner 2 |  | Not Started | 2022-09-07 | 2022-09-21
Workstream 2 | 2.2 | Task2 | Owner 2 |  | Not Started | 2022-09-21 | 2022-10-05
Workstream 2 | 2.3 | Task3 | Owner 2 |  | Not Started | 2022-10-05 | 2022-10-12
Workstream 2 | 2.4 | Task4 | Owner 2 |  | Not Started | 2022-10-12 | 2022-10-26
Workstream 2 | 2.5 | Task5 | Owner 2 |  | Not Started | 2022-10-26 | 2022-11-02
Workstream 2 | 2.6 | Task6 | Owner 2 |  | Not Started | 2022-11-02 | 2022-12-02
Milestone 3 | 3.1 | Task1 | Owner 3 |  | Not Started | 2022-09-15 | 2022-09-29
Milestone 3 | 3.2 | Task2 | Owner 3 |  | Not Started | 2022-09-29 | 2022-10-13
Milestone 3 | 3.3 | Task3 | Owner 3 |  | Not Started | 2022-10-13 | 2022-10-27
Milestone 3 | 3.4 | Task4 | Owner 3 |  | Not Started | 2022-10-27 | 2022-11-10
Milestone 3 | 3.5 | Task5 | Owner 3 |  | Not Started | 2022-11-10 | 2022-11-24
Milestone 3 | 3.6 | Task6 | Owner 3 |  | Not Started | 2022-10-13 | 2022-12-12
Milestone 4 | 4.1 | Task1 | Owner 4 |  | Not Started | 2022-09-06 | 2022-09-30
Milestone 4 | 4.2 | Task2 | Owner 4 |  | Not Started | 2022-09-15 | 2022-09-30
Milestone 4 | 4.3 | Task4 | Owner 4 |  | Not Started | 2022-09-14 | 2022-09-21
Milestone 4 | 4.4 | Task5 | Owner 4 |  | Not Started | 2022-09-21 | 2022-10-10
Milestone 4 | 4.5 | Task6 | Owner 4 |  | Not Started | 2022-10-10 | 2022-10-15
Milestone 4 | 4.6 | #REF! | Owner 4 |  | Not Started | 2022-09-14 | 2022-09-21
Milestone 5 | 5.1 | Task1 | Owner 5 |  | Not Started | 2022-09-08 | 2022-09-22
Milestone 5 | 5.2 | Task2 | Owner 5 |  | Not Started | 2022-09-22 | 2022-10-06
Milestone 5 | 5.3 | Task3 | Owner 5 |  | Not Started | 2022-10-06 | 2022-10-13
Milestone 5 | 5.4 | Task4 | Owner 5 |  | Not Started | 2022-10-13 | 2022-10-20
Milestone 5 | 5.5 | Task5 | Owner 5 |  | Not Started | 2022-10-20 | 2022-11-10
Milestone 5 | 5.6 | Task6 | Owner 5 |  | Not Started | 2022-11-10 | 2022-11-17
Formulas:
Names = 7+[Tracy, Susan]
Names = 7+[Names]