## Instruções
Stakeholder Matrix
by Fabrício Laguna
Filling Instructions
1 | Brainstorm and try to identify all the stakeholders involved with your project and put their name in the first column of the Stakeholders tab.
2 | In the "Interests / Expectations" column, describe what each stakeholder hopes to achieve with the result delivered by the project. It can be something positive like "making a profit" or "improving the quality of the service received", but it can also be something negative like "losing job" or "increasing workload". This column will later help you to identify the position of each stakeholder and establish an appropriate strategy to involve them in the project.
3 | In the Solution column, define how this stakeholder is involved with the solution that will be delivered by the project. If he will be a customer, who will benefit from the solution, if he is an employee of the organization who will have his work affected by the solution or if he is external to the organization and unrelated to the solution. NOTE: A stakeholder can be involved in more than one way. Multiple selection is allowed.
4 | In the Project column, define how the stakeholder is involved with the project requirements. Whether he is a source, a reviewer or if he must approve the requirements. NOTE: A stakeholder can be involved in more than one way. Multiple selection is allowed.
5 | In the influence and impact columns, identify the degree relative to each stakeholder using the qualitative scale: none, little, medium, high or very high. Use the answers in the other columns to decide on the most appropriate grade. Remember that: - Influence refers to the power of the stakeholder in relation to the project. - Impact refers to the degree of benefit that the solution will bring to the stakeholder.
6 | Consult the "Matrix" tab to identify the position of each stakeholder. Based on his position, establish the most appropriate strategy to deal with him (Ignore, Protect, Establish Partnership, Monitor / Move).

## Stakeholders
Stakeholder Matrix
by Fabrício Laguna
Role name | Interests / Expectations | Solution |  |  | Project |  |  | Influence | Impact | Action Strategy . Ignore . Protect . Establish Partnership . Monitor / Move | Influênce (grau) | Importance (grau) | Escale
| or Other comments | Customer | Employee | Extern | Source | Revisor | Approver | [5 empty] | grau | description
House owner | Have privacy; make a profit with your capital investment | X |  |  | X | X | X | high | very high | Establish partnership | 4 | 5 | none | 1
Owner's wife | Having a beautiful home to receive friends | X |  |  | X | X | X | very high | very high | Establish partnership | 5 | 5 | little | 2
Mother in law | Maintain control over the life of the daughter and grandchildren. |  |  | X | X |  |  | high | little | Monitor / move | 4 | 2 | medium | 3
Housekeeper | Have an adequate infrastructure for cooking, washing, ironing. |  | X |  | X | X |  | little | high | Protect | 2 | 4 | high | 4
Providers (water, electricity, tv, telephone) | Have access connections for the provision of services (pipes, cabling, etc.) |  |  | X | X |  |  | none | medium | Protect | 1 | 3 | very high | 5
town hall | Compliance with the laws and regulations established in the master plan and construction code |  |  | X | X |  | X | high | none | Monitor / move | 4 | 1
Children the couple will have | Do not risk accidents. Have leisure options. | X | [5 empty] | none | very high | Protect | 1 | 5
Postman | Quickly deliver mail. |  |  | X | X |  |  | none | none | Ignore | 1 | 1
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A
[11 empty] | #N/A | #N/A

## Matrix
Stakeholder Matrix
by Fabrício Laguna
Stablish partnership
Monitor / Move
Ignore
Protect