## About this workbook
Our Contact details | FB - hudson rickman | hudsonrickman@gmail.com
ABOUT THIS WORKBOOK
Each Sheet is laid out in the same way to make it easier for you to follow.
Taking the RISK sheet as an example, reading down the sheet from the top:
- ROW 3 - We start with a few key points to remember about RISK.
- ROW 4 - We then give you some notes of using this particular sheet.
- ROW 5 - Next is the process to follow for RISKS and we show Process Stages - reading left to right.
The stages are always 1 to 5 and show you the work you would need to do to establish and manage the risks on your project.
- ROW 7 - Is the headers to all the columns in the RISK log.
Columns E, F and G have notes attached to them to give more explanation (just scroll over the cell of each to see the note)
- ROWS 8 to 17 contain examples from real projects of risks and show how they were entered into the log.
What to do after you have established all the risks and their severity.
- Sort Rows 8 to 17 by column G and this will show you the RISKS which require your attention most (those with the highest severity). Why not try it with this workbook?
- Set a review date for those risks with the highest severity score and where applicable allocate the risk to a Team memeber to manage.
- Continue in this manner, updating the details of the columns E,F and G for each RISK as they change during the project.
Any questions - please feel free to email Keith at hudsonrickman@gmail.com - we will respond.

## Project Details
Project Name
Project Short Description
Project Reference
Start Date
Scheduled End Date
Inter Dependencies
Key Risks
Biggest Constraints
Key Assumptions
Our Contact details | FB - hudson rickman | hudsonrickman@gmail.com
PROJECT DETAILS
This sheet captures the details of this project so that any user of the log will know or be able to reference them. This is particularly imporatnt if you put the Log on your network where your team, stakeholders, sponsors may be able to see it. From a communications perspective this is a good approach for you to take as it will contribute to reduced time in meetings and amore conscious use of the Log than would otherwise be achieved.
We have listed what we define as the important details you would need to add as a minimum but of course you can add as much or as little as you want!

## Examples of Risk
Risk Examples
We suggest that you read through the Points to Remember, then the notes on Usage and next follow the Process Stages (left to right), to get a good understanding of how this risk log is used
Points to Remember about RISK |  | Risks are events where there is an uncertainty. This means there are things which you cannot control directly such as the weather, which may have an effect on your project. Other examples of this would be 1. A description of a requirement in a scope document which is vague. 2. A licence not being available to proceed, and you have no control over the issuing of that licence.
Notes on Usage |  | Risk severity (G8) refers to a) the likelihood that the event will occur (E8) and b)the impact on the project if it does occur (F8). You rate each of these and then multiply the two ratings to get a number which is the severity. The numbers you use are up to you - we have included some as an example. There are notes shown in the comment boxes on Cells E8,F8,G8. This process enables you to rank risks. If the likelihood of the event happening and impact to the project are both high, you identify the event as a serious risk. The log includes a description of each risk, analysis and a plan to manage it.
Process Stages |  | Stage 1 and 2 - Identify and Analyse - work with your team members and the stakeholders to identify what the risks are. Then analyse each of them to establish that they are actual risks. List those that are, in this column | Stage 3 - 1. Evaluate: what is the likelihood that this event will occur. Decide a ranking and enter in column E. 2. Then what would be the impact on the project if it did (decide a ranking and enter in column F). 3. Severity (column G) is the product of the rankings of likelihood and impact. |  |  | Stage 4 - Respond: for those risks which you consider you should prepare for (high impact and high likelihood), prepare a plan to minimise the risk to the project if the risk becomes an issue. |  |  | Stage 5 - Monitor: keep the risks under review, monitoring the highest risks more often.
EXAMPLE LOG DETAIL
Risk ID | Date Raised | Risk Description and analysis | Likelihood | Impact | Severity | Mitigation Plan | Owner | Status | Next Review Date | Date Closed
1 |  | Staff Problems - 1. staff leaving, 2. staff turnover, 3. negative staff or team members, 4. morale issues, 5.non availability of staff in the location of where you are working | 5 | 5 | 25 | 1. Fair benefits and terms for all, 2. One on one face time with staff to ensure they are happy; 3. Contracts with HR to make sure they are allocated to you and if not the effect on the project; 4. training for local staff, or cost of bringing in expensive staff from overseas.
2 |  | The licence to continue the project may not be granted | 1 | 5 | 5 | Having no licence granted is clearly a situation where the project could be cancelled. Refer back to stakeholders/sponsors as to how to proceed. Document the outcome of those discussions
3 |  | Key System interfaces may not be compatible | 1 | 5 | 5 | Review with systems staff to define which interfaces, how much work is required and time. Decide if this can be added to your plan without impact. If not define scenarios and ask stakeholders for a decsision
4 |  | The Required level of experienced staff may not be available | 3 | 5 | 15 | Discuss with HR and if the likelihood is high raise this as a key risk and make a contract with HR to retain this member of staff on your project
5 |  | The back up system may not be ready in time for the cutover | 5 | 5 | 25 | This could be a show stopper. Work with PM for the back up system being in place to minimise risk
6 |  | Only one person has the knowledge of the old system | 1 | 3 | 3 | Ensure persons with the knowledge are retained on your project and are unlikely to leave the company - needs consatnt monitoring as pressure on that person may cause them to look to leave or make unacceptable demands on your team and you.
7 |  | Executives fail to support the project | 3 | 5 | 15 | Get to grips with this one by engaging with the Executives and regular communication with them of the status of the project
8 |  | Inaccurate cost forecasts | 1 | 3 | 3 | Monitor as project moves forward. Check that estimates are being adhered to. If not refer to CFO at earliest opportunity
9 |  | Ill defined scope | 5 | 5 | 25 | Always a difficult one. Engage team at early stage of the project to review the scope in details and any areas where the detail is not clear to be referred back to author for clarification asap
10 |  | Change to business strategy | 1 | 5 | 5 | Ask stakeholders to keep this on their agenda and advise you when this changes.
YOUR LOG DETAILS
Note on E8: Likelihood of the risk occuring - assign a score (say) 1 is unlikely and 10 is highly likely. Other scores will be between 1 and 10
Note on F8: Impact on the project - assign a score of (say) 1 is very low impact up to 10 which is very high impact. Other scores will be between 1 and 10
Note on G8: Severity Score = Likelihood Score X Impact Score

## Examples of Assumptions
Assumptions Examples
We suggest that you read through the Points to Remember, then the notes on Usage and next follow the Process Stages (left to right), to get a good understanding of how this Assumption log is used
Points to Remember about Assumptions |  | Assumptions are most often built into the planning stage of the project. They need to be validated as they are just an idea until they are.
Notes on Usage |  | These are any factors that you are assuming to be in place that will contribute to the successful result of your project. The log includes details of the assumption, the reason it is assumed, impact on the project if it is invalid and the action needed to confirm whether the assumption is valid. If it is found to be invalid, a mitigation plan needs to be in place.
Process Stages |  | Stage 1 and 2 - Identify and analyse the assumptions made and the reasons why they were made. | Stage 3 - Evaluate and test the reality of the assumption made |  |  | Stage 4 - Respond |  | Stage 5 - Monitor
EXAMPLE LOG DETAIL
Assumption ID | Date Raised (insert Date) | Assumption Description | Likelihood incorrect? | Impact if Assumption Incorrect | Severity | Mitigation plan | Status | Next Review Date
1 |  | You will get all the resources you need | 5 | 5 | 25 | Establish contract with HR for resource needs. Establish actual resource needs and agree with HR. Test requirements to actual delivery by HR.
2 |  | The delivery of the new computer equipment will be on time | 3 | 5 | 15 | Regular visits to the vendor if possible. If not frequent webinar meetings
3 |  | You will be able to obtain additional project funding in case of need. | 1 | 5 | 5 | Agree with CFO or this has no value
4 |  | All resources will be available for the whole of the project | 3 | 5 | 15 | Agree with HR or this has no value
5 |  | We will have access to 10 skilled specialists throughout the entire project | 5 | 5 | 25 | Validate with HR at start of project
6 |  | Energy resources such as electricity will be available during working hours | 1 | 3 | 3 | Check with the company agent for the utility in question. Devise a back up plan if there is any doubt
7 |  | Materials to complete the project will be readily available to be used | 3 | 5 | 15 | This is not just that the materials/items will be delivered, but that they will function when delivered which is not always the case. Thus if you are installing ATM's you need to pilot one well in advance of delivery date to make sure it works, giving you time to remedy the situation if it does not.
8 |  | The required facilities such as offices and data centre will be made available from day 1 | 1 | 3 | 3 | Meet with your companies Estate Manager (person responsible for offices and the data centre). Explain what is required by your team and get validation from the Estate Manager that they can be provided and where. Documnet this as part of the project documentation..
9 |  | All important stakeholders will be available for the required project meetings | 5 | 5 | 25 | This can be difficult to manage as many stakeholders travel. So each must be approached to see how they can accept or not your meeting schedule. Technology should be employed to ensure that they are inconvenienced as little as possible (which means they may accepot it more readily). If vacations and travel plans get in the way you need to ensure there is a back up plan or person and know who that is.
10 |  | The project Scope will not change | 1 | 5 | 5 | Keeping the scope document from changing can be a most difficult task, and if it does it will have an impact on your project. Treat this assumption with care. Set up a process whereby if the scope is changed you can assess the impact and severity in detail quickly and then present this back to the stakeholders for approval.
Note on E9: Likelihood of the Assumption being INCORRECT. Assign a score of (say) 1 is unlikely and 10 is highly likely. Other scores will be be tween 1 and 10
Note on F9: Impact if assumption is incorrect - Assign a score of (say) 1 is very low impact up to 10 is very high impact. Other scores will be between 1 and 10
Note on G9: Severity = Likelihood Score X Impact Score

## Examples of Issues
Issues Examples
We suggest that you read through the Points to Remember, then the notes on Usage and next follow the Process Stages (left to right), to get a good understanding of how this Issue log is used
Points to Remember about Issues |  | An issue is something that has gone wrong or is going wrong on your project. It is often a Risk which has happened and in this case if it is a key risk you will already have a plan to deal with it. If not in all of the cases below a four step response is required. The four steps are as follows: 1 Get a clear understanding of what has happened. If you had a risk plan has this been activated? 2. Work with your team to work out how you can best deal with this issue, it’s impact and the priority this item has within the overall framework of the project. 3. Decide what to do about it and communicate with team members and if necessary executive management 4. Document the plan to resolve the issue and monitor to completion. Once this is resolved see what lessons can be learned to minimise risk of this happening again.
Notes on Usage |  | Something that is going wrong on your project and needs to be managed. Failure to manage issues may result in a poor delivery or even failure. The log includes a description of each issue, the impact it is having, its seriousness and actions needed to contain and remove/mitigate it.
Process Stages |  | Stage 1 and 2 - Identify the Issue and the impact on the project of this issue. | Stage 3 - Evaluate |  |  | Stage 4 - Respond/Remove/Mitigate |  |  | Stage 5 - Monitor
EXAMPLE LOG DETAIL
Issue ID | Date Raised | Issue Description | Impact | Priority | Severity | Mitigation Plan | Owner | Status | Review Date
1 |  | Key project resource has been taken ill and will be absent for the next two weeks | 5 | 5 | 25 | Can the delay be accomodated?
2 |  | Poor quality of deliverables | 5 | 5 | 25 | Major issue which may not be rcoverable - early testing can avoid this in future
3 |  | Scope creep (stakeholders request a change to the scope) | 3 | 5 | 15 | Evaluate as you would any other issue and advise stakeholder of the effct of the request
4 |  | Software not working at point of delivery | 3 | 5 | 15 | Major issue which may not be rcoverable - early testing can avoid this in future
5 |  | Change management overload | 5 | 5 | 25 | This can possibly cause the project to fail. Change management is a process to go through and if too much change is required over too short a time then the outcome may be a non delivery of the project. Plan for this at the outset.
6 |  | Design issues - the design does not work | 1 | 3 | 3 | Refer back to the design manager for estimates of time to correct (if possible),and advise the Sponsor/stakeholders of the impact.
7 |  | Integration is taking too long | 3 | 5 | 15 | Get the team together to establish what the issue is and how to resolve it.
8 |  | Technical resources are not performing to schedule | 1 | 3 | 3 | Establish why with the technical resources and see if you can manage to re-organize to resolve this issue or is it just a need for more resources?
9 |  | Resistance to change by stakeholder community | 5 | 5 | 25 | Early communication of the changes is essential or this can happen. If it still does happen then refer this to the project sponsor to resolve
10 |  | Benefit shortfall - during the project and at delivery time | 1 | 5 | 5 | Can be an issue that the scoped deliverable just does not provide the benefit. Early definition of the benefit to be delivered will help to obviate this. It is best not to leave this until the end of the project but test it as you go forward in the project
Note on E8: Impact of this issue on the Project. Assign a score of (say) 1 is low impact and up to 10 which is high impact. Other scores will be between 1 and 10
Note on F8: The priority of resolving this issue. Assign a score (say) 1 is low priority and 10 is high priority. Other scores will be between 1 and 10
Note on G8: Severity of this issue to the project = Impact Score X Priority Score

## Examples of Dependencies
Dependencies Examples:
We suggest that you read through the Points to Remember, then the notes on Usage and next follow the Process Stages (left to right), to get a good understanding of how this dependency log is used
Points to Remember about Dependencies |  | Dependencies can be internal or external.Internal dependencies are between members of your team or other teams within your company who have to deliver to your project. External dependencies are between your project and an external supplier to your project (say) of ATMs or software. There are four types of task dependencies. Finish to Start; Finish to Finish; Start to Start: Start to Finish; - for more details see the definitions in D14 to D17
Notes on Usage |  | Any event or work deliverable that is either dependent on the result of your project , or your project depends on for success. The log captures who you are dependent upon, what they should deliver to you and when. It should also capture who is dependent on you for your deliverables. In reality you are managing the risk of non completion of the dependency, not the dependency itself.
Process Stages |  | Stage 1 and 2 - Identify and Analyse the dependency | Stage 3 - Evaluate |  |  | Stage 4 - Respond |  |  | Stage 5 - Monitor
EXAMPLE LOG DETAIL
ID | Date Raised | Dependency Description | Likelihood or risk of Non Completion of the dependency | Impact of non completion | Severity | Mitigation or Risk Management Plan | Status | Date | Owner
1 |  | LOGICAL: The foundations of a house cannot be laid until the architectural diagrams are available | 5 | 5 | 25 | Work with the architect (company) to ensure delivery in accordance with the required schedule, regular meetings help
2 |  | RESOURCE BASED - depends on how many resources we need against what we have and their skill sets | 1 | 5 | 5 | Manage the risk by working closely with HR department so they understand the risk
3 |  | DISCRETIONARY: Often depends on the preferences of the work force - if you have a house being built then a painter may wish to paint each room in turn or do the ceilings in every room first | 1 | 5 | 5 | Providing the painter (in this case) can deliver the work by the scheduled time this will not effect your project, but if he/she cannot then a sit down on site discussion is needed
4 |  | INTERNAL - Your project is dependent on another project in the company delivering to your project a system they are building. | 3 | 5 | 15 | Here you need to establish a working relationship with the project manager of this other project in your company.He/she needs to be aware of the knock on effect of that projects late delivery or even lack of benefits and quality.
5 |  | EXTERNAL - a company has to deliver 25 ATM machines before you can implement an ATM network for your company | 5 | 5 | 25 | Here you need to establish a working relationship with the project manager of this other projector company. He/she needs to be aware of the knock on effect of that projects late delivery or even lack of benefits and quality.
6 |  | GLOBAL - Your project is part of a global project to implement a new system across the company worldwide. This is being managed by a Team in Head office. Your roll out project is dependent on this team carrying out their activities and tasks to schedule | 1 | 3 | 3 | In this case you really need to be part of this team in Head Office or have very frequent status calls with them and they need to communicate to you their status.
7 |  | TASK DEPENDENCIES TYPE 1: Finish to start - the first task must complete before the second task can start - you cannot build the roof on a house until the walls are in place, write code for module 1 must be completed before test module 1 can commence | 3 | 5 | 15 | Establish the slack available between these two tasks if there is any. Monitor the task which has to finish first to ensure that if there is any delay beyond the slack, that you are aware of this at the earliest time and can either manage this away or accept it has no impact on the next task.
8 |  | TASK DEPENDENCIES TYPE 2: Finish to Finish - the second task cannot finish before the first task finishes -All code tested cannot finish before the task "test code of module z", the last task. | 1 | 3 | 3 | Any delay in the first tasks, (testing of various code being written) will delay the overall task of "All code tested". Monitoring each of the individual tasks of writing code will enable you to see if the deadline for the Overall task (all code tested) will be reached on time.
9 |  | TASK DEPENDENCIES TYPE 3: Start to start - the second task cannot start until the first task starts - the task write manual must start before task write chapter 1 of manual | 5 | 5 | 25 | Getting the resources in place to start the writing of the manual may be an issue, which will delay the commencement of writing chapter 1 (in this example). Prudent approach to initial planning will show these dependencies and allow you to plan well ahead of time for the resources to be in place.
10 |  | TASK DEPENDENCIES TYPE 4: Start to finish - the first task must start before the second task can finish - the task assign coder for module 3 must start before the task all work assigned can finish | 1 | 5 | 5 | This dependency relationship is not used very often but when it is used there is a need to monitor all of the individual tasks to ensure thay are started in order for the overall task to be finished. As with Type 3 this is a case of prudent planning and monitoring being required.
Note on E7: Non Completion Risk - assign a score of (say) 1 is low risk and 10 is high risk. Any other scores will be between 1 and 10
Note on F7: Impact on the project of non completion. Assign a score of (say) 1 is low impact to 10 which is high impact. Any other scores will be between 1 and 10
Note on G7: Severity = Likelihood score X impact score

## Examples of Constraints
Constraints Examples
We suggest that you read through the Points to Remember, then the notes on Usage and next follow the Process Stages (left to right), to get a good understanding of how this Issue log is used
Points to Remember about Constraints |  | Six basic Constraints exist usually. 1. Time (schedule), 2. Budget, 3. Scope to which has recently been added 4. Quality of deliverable, 5. Benefit and 6. Risk tolerance range. Our examples show how these manifest themselves in real life situations
Notes on Usage |  | Any stipulation by Project Stakeholders which will directly effect the result of your project. The log captures what the constraint is, it's effect on the project and plans to ensure the constraint is complied with.
Process Stages |  | Stage 1 and 2 - Identify and Analyse. List Constraint Details in this column | Stage 3 - Evaluate |  |  | Stage 4 - Respond | Stage 5 - Monitor
EXAMPLE LOG DETAIL
ID | Date Raised | Constraint Description | Impact on Project | Importance | Severity | Plan to comply | Status
1 |  | TIME - Project must be completed within 60 days | 5 | 5 | 25 | Carry. Out initial planning against this constraint. Analyse probability of completion. If not possible then refer back to the sponsor and stakeholders
2 |  | RESOURCES - Only one resource with the required knowledge is available to your team | 1 | 5 | 5 | Establish a contract with HR and the Line Manager of this resource. Show effect of removal of this resource from the project
3 |  | RESOURCES -You have to work with the given resources | 1 | 5 | 5 | Carry out initial planning with this resource level. If project aims are achievable within risk limits, fine, if not go back to the stakeholders and advise the risk
4 |  | RESOURCES -You will only have access to one software engineer during the project | 3 | 5 | 15 | Establish a contract with HR and the Line Manager of this resource. Show effect of removal of this resource from the project
5 |  | BUDGET - Under no circumstances can the budget overrun | 5 | 5 | 25 | Manage costs against budgeted costs on frequent basis but at least monthly. Project costs forward based on the current run rate, and the budgeted run rate.Highlight differences as early as possible and see if any negative differences (overruns) can be handled within the budget or not. If they cannot then this has to be raised to sponsors/stakeholders with a reasoned argument or other segments of the project reduce their costs to make the net situation viable
6 |  | The executive management team lacks commitment | 1 | 3 | 3 | A common constraint on the project as this means longer times for decision making at their level, if at all. Start the project as you mean to go on by regular and frequent communications with the executive management team.
7 |  | Company re-organisation during the project | 3 | 5 | 15 | This may well lead to resources not being available to your project at a crucial time. Establish with your executive management the need for early warning and where this is a key risk raise this to them at the earliest time but with a clear definition of what this will mean and how you intend to get round it.
8 |  | Major holidays during the project | 1 | 3 | 3 | Ensure adequate research is taken on this point during the planning stage
9 |  | Unrealistic expectation from stakeholders | 5 | 5 | 25 | Communications of the project status on a regular basis is essential
10 |  | Quality of deliverable | 5 | 5 | 25 | This has to be monitored from the start of the project, and during the project, not waiting until the end when the deliverables are actually delivered. Establish a program within the project to monitor this at all times. Consider use of a pilot approach - in our ATM example ask for one to be delivered early so that it can be tested to see if the benefit can be achieved. Rejection at the time of delivery means project failure, not an option
11 |  | Benefits achievable from this project | 2 | 5 | 10 | Initially this has to be defined in detail - it should be in the scope document. Once it has been defined then you need to establish a program or process within the project to ensure that the benefits are going to be delivered. Monitor this as a deliverable rather than a constarint.
12 |  | Risk Tolerance Range | 4 | 5 | 20 | Establish a risk tolerance range with the sponsor/ executive team at the outset of the project. This will then give you the benchmark you need to monitor against as the project proceeds
Note on E7: Impact of this constraint on the project. Assign a score of 1 is low impact to 10 is high impact. Other scores will be between 1 and 10a
Note on F7: Importance of this constraint. Assign a score of 1 is very low impact up to 10 is very high impact. Other scores will be between 1 and 10
Note on G7: Severity of this constraint = Impact Score X Importance Score