## Dashboard
srl | Task Description | Sec | Dept | A STRT | A END | % | srl | Issue | Score | Owner | Comments
1 | Activity 01 | BTS | Civil | 2020-01-01 | 2020-01-15 | 100% | 1 | Issue#5 | 3603.6 | Ahmad | No response from the contractor
2 | Activity 04 | CFA | Acrhitict | 2020-02-06 | 2020-02-27 | 100% | 2 | Issue#13 | 2244.32 | Ahmad | Next week meeting
3 | Activity 07 | BTS | Civil | 2020-02-17 | 2020-03-05 | 100% | 3
4 | Activity 08 | ELC | Electrical | 2020-03-03 | 2020-03-16 | 100% | 4
Formulas:
A STRT = INDEX(Lists!$B17:W47,Dashboard!$[srl],MATCH(F30,Lists!$B16:W16,0))
A END = INDEX(Lists!$B17:W47,Dashboard!$[srl],MATCH(G30,Lists!$B16:W16,0))
Actual
Plan
Medium Priotity Issues
4
2
Done Tasks
X Project Dashboard
Budget
$2,900,000
Plan
$2,085,000
Acutal
$1,855,000
10-Apr-2020

## Tasks
[5 empty] | Start Date: | 2020-01-01 | End Date: | 2020-07-16 | Duration | 197 | Today: | 2020-04-10 | 100 | Days From Start: | 100
Task Description | Sec | Dept | P STRT | P Duration (WD) | P END | P (CD) | A STRT | A Duration (WD) | A END | A (CD) | % | %Days | Days From A Start | Schedual Status | Resources | P Cost | A Cost | % C | Budget Status | SRL | Today |  | Holidays | Section | Department
Activity 01 | BTS | Civil | 2020-01-01 | 10 | 2020-01-15 | 14 | 2020-01-01 | 10 | 2020-01-15 | 14 | 100% | 14 | 100 | Done |  | 4308 | 4308 | 4308 |  | 20 | 2020-04-10 | 3 | 2019-02-05 | BTS | Civil
Activity 02 | BTS | Civil | 2020-01-16 | 20 | 2020-02-13 | 28 | 2020-01-16 | 20 | 2020-02-13 | 28 | 80% | 22.4 | 85 | Delayed |  | 1336 | 1336 | 1068.8 |  | 19 | 2020-04-10 | 1000 | 2019-03-25 | ARC | Acrhitict
Activity 03 | ARC | Acrhitict | 2020-02-04 | 17 | 2020-02-27 | 23 | 2020-02-04 | 17 | 2020-02-27 | 23 | 90% | 20.7 | 66 | Delayed |  | 3278 | 3278 | 2950.2 |  | 18 | 2020-04-10 | 1000 |  | CFA | Acrhitict
Activity 04 | CFA | Acrhitict | 2020-02-06 | 15 | 2020-02-27 | 21 | 2020-02-06 | 15 | 2020-02-27 | 21 | 100% | 21 | 64 | Done |  | 2758 | 2758 | 2758 |  | 17 | 2020-04-10 | 6 |  | GRD | Electrical
Activity 05 | ARC | Acrhitict | 2020-02-09 | 8 | 2020-02-19 | 10 | 2020-02-09 | 8 | 2020-02-19 | 10 | 95% | 9.5 | 61 | Delayed |  | 2547 | 2547 | 2419.65 |  | 16 | 2020-04-10 | 1000 |  | ELC | Electrical
Activity 06 | GRD | Electrical | 2020-02-10 | 7 | 2020-02-19 | 9 | 2020-02-10 | 7 | 2020-02-19 | 9 | 90% | 8.1 | 60 | Delayed |  | 2183 | 2183 | 1964.7 |  | 15 | 2020-04-10 | 1000 |  | CVL | Civil
Activity 07 | BTS | Civil | 2020-02-17 | 13 | 2020-03-05 | 17 | 2020-02-17 | 13 | 2020-03-05 | 17 | 100% | 17 | 53 | Done |  | 4662 | 4662 | 4662 |  | 14 | 2020-04-10 | 9
Activity 08 | ELC | Electrical | 2020-03-02 | 9 | 2020-03-15 | 13 | 2020-03-03 | 9 | 2020-03-16 | 13 | 100% | 13 | 38 | Done |  | 2010 | 2010 | 2010 |  | 13 | 2020-04-10 | 10
Activity 09 | CVL | Civil | 2020-03-07 | 14 | 2020-03-25 | 18 | 2020-03-08 | 14 | 2020-03-26 | 18 | 95% | 17.1 | 33 | Delayed |  |  |  | 0 |  | 12 | 2020-04-10 | 1000
Activity 10 | ELC | Electrical | 2020-03-14 | 13 | 2020-03-31 | 17 | 2020-03-15 | 13 | 2020-04-01 | 17 | 90% | 15.3 | 26 | Delayed |  |  |  | 0 |  | 11 | 2020-04-10 | 1000
Activity 11 | CVL | Civil | 2020-03-14 | 29 | 2020-04-22 | 39 | 2020-03-15 | 29 | 2020-04-23 | 39 | 90% | 35.1 | 26 | In Progress |  |  |  | 0 |  | 10 | 2020-04-10 | 1000
Activity 12 | CVL | Civil | 2020-03-16 | 30 | 2020-04-27 | 42 | 2020-03-17 | 30 | 2020-04-28 | 42 | 70% | 29.4 | 24 | In Progress |  |  |  | 0 |  | 9 | 2020-04-10 | 1000
Activity 13 | CFA | Acrhitict | 2020-03-31 | 13 | 2020-04-19 | 19 | 2020-04-01 | 13 | 2020-04-20 | 19 | 90% | 17.1 | 9 | In Progress |  |  |  | 0 |  | 8 | 2020-04-10 | 1000
Activity 14 | BTS | Civil | 2020-04-13 | 26 | 2020-05-19 | 36 | 2020-04-14 | 26 | 2020-05-20 | 36 | 10% | 3.6 | -4 | Not Started |  |  |  | 0 |  | 7 | 2020-04-10 | 1000
Activity 15 | CVL | Civil | 2020-04-18 | 24 | 2020-05-20 | 32 | 2020-04-19 | 24 | 2020-05-21 | 32 |  | 0 | -9 | Not Started |  |  |  | 0 |  | 6 | 2020-04-10 | 1000
Activity 16 | BTS | Civil | 2020-05-03 | 24 | 2020-06-04 | 32 | 2020-05-04 | 24 | 2020-06-07 | 34 |  | 0 | -24 | Not Started |  |  |  | 0 |  | 5 | 2020-04-10 | 1000
Activity 17 | ARC | Acrhitict | 2020-05-27 | 19 | 2020-06-23 | 27 | 2020-05-28 | 19 | 2020-06-24 | 27 |  | 0 | -48 | Not Started |  |  |  | 0 |  | 4 | 2020-04-10 | 1000
Activity 18 | BTS | Civil | 2020-06-11 | 13 | 2020-06-30 | 19 | 2020-06-12 | 13 | 2020-06-30 | 18 |  | 0 | -63 | Not Started |  |  |  | 0 |  | 3 | 2020-04-10 | 1000
Activity 19 | ARC | Acrhitict | 2020-06-13 | 14 | 2020-07-01 | 18 | 2020-06-14 | 14 | 2020-07-02 | 18 |  | 0 | -65 | Not Started |  |  |  | 0 |  | 2 | 2020-04-10 | 1000
Activity 20 | ELC | Electrical | 2020-06-16 | 22 | 2020-07-16 | 30 | 2020-06-17 | 22 | 2020-07-19 | 32 |  | 0 | -68 | Not Started |  |  |  | 0 |  | 1 | 2020-04-10 | 1000
Activity 21 | ELC | Electrical | 2020-06-21 | 6 | 2020-06-29 | 8 | 2020-06-22 | 6 | 2020-06-30 | 8 |  | 0 | -73 | Not Started |  | 3213 | 3213 | 0 |  | 0 | 2020-04-10 | 1000
85.71%
Formulas:
P STRT = [P STRT, row above]+15
P END = IF(OR(ISBLANK(Tasks!$[P STRT]),ISBLANK(Tasks!$[P Duration (WD)])),"",WORKDAY.INTL(Tasks!$[P STRT],Tasks!$[P Duration (WD)],7,Table4[Holidays]))
A END = IF(OR(ISBLANK(Tasks!$[A STRT]),ISBLANK(Tasks!$[A Duration (WD)])),"",WORKDAY.INTL(Tasks!$[A STRT],Tasks!$[A Duration (WD)],7,Table4[Holidays]))
Project Tracker

## Budget Plan
Plan | TRUE |  | Current Month | 2020-04-01 |  | Planned Cost | 2085000
Actual | TRUE |  |  |  |  | Acutal Cost | 1855000
Work Desc | Plan/Actual | Element Budget | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01
Total | Plan | 2900000 | 620000 | 1160000 | 1660000 | 2085000 | 2430000 | 2685000 | 2900000
Total | Actual | 0 | 640000 | 1165000 | 1690000 | 1855000 | #N/A | #N/A | #N/A
Cumulative | Plan | 2900000 | 620000 | 1160000 | 1660000 | 2085000 | 2430000 | 2685000 | 2900000
Cumulative | Actual | 0 | 640000 | 1165000 | 1690000 | 1855000 | 1855000 | 1855000 | 1855000
Total | Plan | 2900000 | 620000 | 540000 | 500000 | 425000 | 345000 | 255000 | 215000
Total | Actual | 0 | 640000 | 525000 | 525000 | 165000 | 0 | 0 | 0
Work Desc | Plan/Actual | Element Budget | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | Remaining
Architect | Plan | 200000 | 50000 | 50000 | 30000 | 30000 | 20000 | 10000 | 10000 | 0
Architect | Actual |  | 40000 | 30000 | 60000 | 25000
Civil Work | Plan | 2000000 | 450000 | 370000 | 350000 | 270000 | 230000 | 180000 | 150000 | 0
Civil Work | Actual |  | 500000 | 390000 | 340000 | 20000
Salaries | Plan | 500000 | 75000 | 75000 | 85000 | 90000 | 75000 | 55000 | 45000 | 0
Salaries | Actual |  | 70000 | 70000 | 75000 | 80000
Tools | Plan | 200000 | 45000 | 45000 | 35000 | 35000 | 20000 | 10000 | 10000 | 0
Tools | Actual |  | 30000 | 35000 | 50000 | 40000

## Issues
Issues | [11 empty] | 2 | Medium
|  |  | Contingency Reserve | 26855.3
srl | Issue | Probability | Impact | Score | Priority | Owner | Open Date | Close Date | Comments | Status |  | Score | Priority | Opened Issues
1 | Issue#1 | 46% | 1353 | 622.38 | Low | Akram |  |  | Waiting Vendor feedback | Open | 10000 | 0 | Low | 4
2 | Issue#2 | 23% | 8703 | 2001.69 | Medium | Ashraf |  |  | Solved without extra cost | Close | 10000 | 2000 | Medium | 2
3 | Issue#3 | 33% | 2127 | 701.91 | Low | Ashraf |  |  | Solved wih the owner | Close | 10000 | 4000 | High | 1
4 | Issue#4 | 53% | 3019 | 1600.07 | Low | Ashraf |  |  | Solved wih the owner | Close | 10000
5 | Issue#5 | 90% | 4004 | 3603.6 | Medium | Ahmad |  |  | No response from the contractor | Open | 8
6 | Issue#6 | 9% | 4436 | 399.24 | Low | Ashraf |  |  | Most likely solved with no cost | Open | 10000
7 | Issue#7 | 4% | 1206 | 48.24 | Low | Ahmad |  |  | Solved wih the owner | Close | 10000
8 | Issue#8 | 46% | 1318 | 606.28 | Low | Akram |  |  | Solved wih the owner | Close | 10000
9 | Issue#9 | 17% | 3187 | 541.79 | Low | Ahmad |  |  | Most likely solved with no cost | Open | 10000
10 | Issue#10 | 12% | 9007 | 1080.84 | Low | Ahmad |  |  | Solved wih the owner | Close | 10000
11 | Issue#11 | 62% | 9771 | 6058.02 | High | Akram |  |  | High risk, need high mangement | Open | 10000
12 | Issue#12 | 47% | 9044 | 4250.68 | High | Akram |  |  | Solved by paying3500 $ | Close | 10000
13 | Issue#13 | 26% | 8632 | 2244.32 | Medium | Ahmad |  |  | Next week meeting | Open | 16
14 | Issue#14 | 35% | 3232 | 1131.2 | Low | Ashraf |  |  | 1500 $ payed | Close | 10000
15 | Issue#15 | 56% | 2006 | 1123.36 | Low | Ashraf |  |  | to be discussed with the owner | Open | 10000
16 | Issue#16 | 21% | 4008 | 841.68 | Low | Akram |  |  | Closed without extra cost | Close | 10000

## Lists
| 4 | [21 empty] | 2
| Done | Done Tasks | [20 empty] | Medium | Medium Priotity Issues
| Scroll Value | 1 | [11 empty] | 5 | [8 empty] | Scroll Value | 1
| Schedule Status | Count | [11 empty] | Total | [8 empty] | Priority | Opened Issues
| Not Started | 8 | [11 empty] | Work Desc | [8 empty] | Low | 4
| Delayed | 6 | [11 empty] | Architect | [8 empty] | Medium | 2
| In Progress | 3 | [11 empty] | Civil Work | [8 empty] | High | 1
| Done | 4 | [11 empty] | Salaries
Tools
Total
4 | Task Description | Sec | Dept | P STRT | P Duration (WD) | P END | P (CD) | A STRT | A Duration (WD) | A END | A (CD) | % | %Days | Days From A Start | Schedual Status | Resources | P Cost | A Cost | % C | Budget Status | SRL | Today | 2 | srl | Issue | Probability | Impact | Score | Priority | Owner | Open Date | Close Date | Comments | Status
1 | Activity 01 | BTS | Civil | 2020-01-01 | 10 | 2020-01-15 | 14 | 2020-01-01 | 10 | 2020-01-15 | 14 | 100% | 14 | 100 | Done | 0 | 4308 | 4308 | 4308 | 0 | 20 | 2020-04-10 | 1 | 5 | Issue#5 | 0.9 | 4004 | 3603.6 | Medium | Ahmad | 0 | 0 | No response from the contractor | Open
2 | Activity 04 | CFA | Acrhitict | 2020-02-06 | 15 | 2020-02-27 | 21 | 2020-02-06 | 15 | 2020-02-27 | 21 | 100% | 21 | 64 | Done | 0 | 2758 | 2758 | 2758 | 0 | 17 | 2020-04-10 | 2 | 13 | Issue#13 | 0.26 | 8632 | 2244.32 | Medium | Ahmad | 0 | 0 | Next week meeting | Open
3 | Activity 07 | BTS | Civil | 2020-02-17 | 13 | 2020-03-05 | 17 | 2020-02-17 | 13 | 2020-03-05 | 17 | 100% | 17 | 53 | Done | 0 | 4662 | 4662 | 4662 | 0 | 14 | 2020-04-10 | 0
4 | Activity 08 | ELC | Electrical | 2020-03-02 | 9 | 2020-03-15 | 13 | 2020-03-03 | 9 | 2020-03-16 | 13 | 100% | 13 | 38 | Done | 0 | 2010 | 2010 | 2010 | 0 | 13 | 2020-04-10 | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0
0 | [22 empty] | 0

## SpeedoMeters
Project Scope Status |  | Project Schedule Status |  | Project Cost Status
Completed | 85.71% | Completed | 50.76% | Completed | 63.97%
In Progress | 14.29% | In Progress | 49.24% | In Progress | 36.03%
Total | 100% | Total | 100% | Total | 100%
Pointer Settings |  | Pointer Settings |  | Pointer Settings
Completed | 85.71% | Completed | 50.76% | Completed | 63.97%
Needle Size | 1% | Needle Size | 1% | Needle Size | 1%
200% Remaining | 113.3% | 200% Remaining | 148.2% | 200% Remaining | 135%
Lables Settings |  | Lables Settings |  | Lables Settings
20% | 10% | 20% | 10% | 20% | 10%
20% | 30% | 20% | 30% | 20% | 30%
20% | 50% | 20% | 50% | 20% | 50%
20% | 70% | 20% | 70% | 20% | 70%
20% | 90% | 20% | 90% | 20% | 90%
100% | 100% | 100% | 100% | 100% | 100%