## Guideline
What are the contents that 5D BIM implementation plan should be included?
1 | Objectives and Goals
Clearly define the objectives and goals of the 5D BIM implementation plan. What are you trying to achieve with the implementation? Ensure that the objectives are specific, measurable, attainable, relevant, and time-bound (SMART).
2 | Roles and Responsibilities
Identify the key PIC and their roles and responsibilities in the 5D BIM implementation process. This includes both the implementation team members and any other individuals or departments involved in the project.
3 | Training and Support
Determine the training needs of the members involved in the implementation, such as endusers, customers, or downstream. Develop a training plan to provide the necessary skills and knowledge required for a successful implementation. Also, seek support from Glodon to fulfil needs.
4 | Performance Monitoring and Evaluation
Establish metrics and key performance indicators to measure the success of the implementation. Elaborate on how your organization conducts performance monitoring when adopting 5D BIM
5 | Current Achievements and Future Plan
Provide a brief overview of the current achievements in your organization after implementing 5D BIM. Analyse the gaps between the goals set and the actual achievements and develop an optimization plan accordingly.

## Notes
IMPORTANT NOTES
1 | Each implementation plan may have specific requirements depending on your own organization chart. It's important to tailor the plan to meet the unique needs of your organization or situation.
2 | The implementation of 5D BIM should not be solely reliant on individual teams or quantity surveyors; it should be a strategic decision made by the entire organization. The implementation plan aims to assess the company's capability and strategy for continuous utilization.
3 | The 5D BIM implementation plan is not solely for submission purposes but also serves as a guiding document for future and improved 5D BIM in your organization.
4 | You are welcome to utilize the provided template and populate the answers within the designated table, or alternatively, you have the flexibility to add, modify, attach or incorporate your own BIM Implementation Plan as deemed necessary

## Plan
5D BIM IMPLEMENTATION PLAN
| Question | Explanation | Example | Answer
1 | Identify the 5D BIM Uses & Expected 5D BIM Outcome | Identify your 5D BIM use in the construction phases and the expected outcome from the BIM tools based on the company principles. | -Pre-contract, post-contract stage use​ - Output results expected​ - Current workflow to digitalise
2 | Select the appropriate BIM Tools software and hardware | Choose the BIM software that best suits your company/project needs. | - BIM Project requirement​ - Based on company requirement, budget and preference​ - Shortlist/analyse software with strength​ - Software learning
3 | 5D Data Requirements & Data Input | Determine what data is required to integrate to the new tools used. This includes information about materials, labor, equipment, and other project costs based on company practice. | - QTO data needed​ - Costing data​ - Tendering method and flow
4 | Develop Data Management Plan | Establish protocols for collecting, organizing, and managing the data required for cost estimating. This may involve creating a centralized database or using cloud-based storage. | - Develop infrastructure and centralised database to store data
5 | Completion of Pilot Project | Create a project model based on the project details using the 5D BIM tool. The project output should include with all necessary 5D quantification & costing info. | - Identify the team​ - Pilot testing based on real project​ - Set a timeline​ - Analyse results based on certain dimension​
6 | Design the 5D BIM Project Execution Process | Develop a process which includes tasks & people involved in the 5D BIM project along with project setup guidelines using the 5D BIM tools. | - Define roles & responsibility​ - Explain each process involved and all the deliverables needed based on project scope (Project naming, Mega project management)​