## Sheet2
| Owner: | NorthStar Development |  |  | Date: | DATE: 5/31/20 Rev #0
| Job Name: | Specter Villas |  |  | Phased? | No | Nightshifts? | No
| PM: | John Titus |  |  | Occupied? | No
| Super: | Guy Normus |  |  | Contract Amt: | 4000000 | $/Mo | 328767.1233
| Architect: |  |  |  | Sq Ft: | 75000 | Floors/levels: | 3
| Engineer: |  |  |  | GC's | 320000 | GC's/Mo | 26301.3699
DESCRIPTION |  | START | FINISH | CAL DAYS | WEEKS | MONTHS | NOTES
OVERALL |  | 2019-01-01 | 2020-01-01 | 365 | 52.1429 | 12.1667
General |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Request for Qualification (RFQ) |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Request for Proposal (RFP) |  |  |  | 0 | 0 | 0
Contract Negotiation |  |  |  | 0 | 0 | 0
Notice of Award |  |  |  | 0 | 0 | 0
Notice to Proceed |  |  |  | 0 | 0 | 0
Mobilization |  |  |  | 0 | 0 | 0
Design |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Conceptual Design |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Review/approve Conceptual Design |  |  |  | 0 | 0 | 0
Schematic Design (SD) |  |  |  | 0 | 0 | 0
Review/approve SD's |  |  |  | 0 | 0 | 0
Design Development (DD'S) |  |  |  | 0 | 0 | 0
Review/approve DD's |  |  |  | 0 | 0 | 0
Construction Documents (CD's) |  |  |  | 0 | 0 | 0
Review/approve CD's |  |  |  | 0 | 0 | 0
Permitting |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Plan review |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Response to comments |  |  |  | 0 | 0 | 0
Review comments |  |  |  | 0 | 0 | 0
Sitework |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Grading |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Utilities |  |  |  | 0 | 0 | 0
Curb & Gutter |  |  |  | 0 | 0 | 0
First lift ashpalt |  |  |  | 0 | 0 | 0
Finish lift asphalt |  |  |  | 0 | 0 | 0
Off-site work |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Deceleration lanes |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Street improvements |  |  |  | 0 | 0 | 0
Traffic signals |  |  |  | 0 | 0 | 0
Buildings |  | 2019-01-01 | 2020-01-01 | 365 | 52.1429 | 12.1667
Underground |  | 2019-01-01 | 2019-02-01 | 31 | 4.4286 | 1.0333
Foundations |  |  |  | 0 | 0 | 0
Elevation 100'-0" |  |  |  | 0 | 0 | 0
Superstructure |  | 2019-12-30 | 2020-01-01 | 2 | 0.28571 | 0.066667
Formulas:
NorthStar Development = MIN([NorthStar Development, row below]:C57)
FINISH = MAX([FINISH, row below]:D57)
CAL DAYS = +DAYS([FINISH],[NorthStar Development])