## Details
Project ID | Project Name | PM ID | Project Status | Start Date (BL) | End Date (BL) | Progress | Budget Without VAT | External/Internal
10000 - STG - PM005 | Project Sunrise | PM005 | OnHold | 2023-11-21 | 2025-01-18 | 84% | 552124 | Internal
10001 - STG - PM030 | Passion Chasers | PM030 | Delayed | 2023-05-17 | 2023-07-06 | 93% | 90008379 | External
10002 - DSN - PM029 | Phoenix: Redesigning a struggling product/service | PM029 | Delayed | 2023-10-01 | 2023-12-25 | 52% | 39184554 | External
10003 - INV - PM024 | Capital Catalyst | PM024 | Not Started | 2025-07-01 | 2025-10-28 | 0% | 99557460 | External
10004 - INV - PM014 | Merger Majesty | PM014 | Not Started | 2025-02-01 | 2025-03-25 | 0% | 84960573 | Internal
10005 - IMP - PM015 | Network Nexus | PM015 | Not Started | 2024-06-03 | 2024-10-20 | 19% | 28047241 | Internal
10006 - STG - PM019 | Project Odyssey | PM019 | Closed | 2024-01-23 | 2024-01-30 | 100% | 37317280 | External
10007 - INV - PM029 | Wealth Wave | PM029 | Closed | 2023-08-05 | 2023-09-19 | 100% | 20677128 | Internal
10008 - FIN - PM001 | Financial Odyssey | PM001 | OnHold | 2023-10-12 | 2024-11-25 | 12% | 56159886 | Internal
10009 - FIN - PM028 | Capital Quest | PM028 | OnGoing | 2023-08-09 | 2025-01-10 | 46% | 38023238 | External
10010 - STG - PM005 | Project Stellar | PM005 | OnHold | 2023-09-22 | 2024-01-24 | 18% | 6907884 | External
10011 - IMP - PM023 | Project Connect | PM023 | OnGoing | 2023-09-11 | 2025-01-15 | 10% | 98306794 | Internal
10012 - SEC - PM014 | Cyber Sentinel | PM014 | OnGoing | 2024-01-18 | 2026-03-06 | 92% | 44953691 | Internal
10013 - INV - PM003 | Finance Frontier | PM003 | OnHold | 2023-03-28 | 2024-03-15 | 69% | 76755253 | External
10014 - IMP - PM029 | Data Highway | PM029 | Not Started | 2024-10-01 | 2025-03-27 | 0% | 44426947 | External
10015 - STG - PM025 | Project Victory | PM025 | Delayed | 2023-08-01 | 2023-10-02 | 39% | 8208269 | Internal
10016 - PLN - PM025 | Project Blueprint | PM025 | OnGoing | 2023-03-28 | 2024-10-02 | 48% | 24064608 | Internal
10017 - HRM - PM007 | Talent Trailblazers | PM007 | Delayed | 2023-10-24 | 2023-12-14 | 25% | 62143917 | External
10018 - PLN - PM018 | Strategic Navigator | PM018 | Not Started | 2024-04-26 | 2025-09-17 | 14% | 17318328 | External
10019 - HRM - PM004 | Culture Catalysts | PM004 | Not Started | 2025-12-04 | 2027-03-24 | 7% | 24120341 | External
10020 - PLN - PM014 | PlanCrafters | PM014 | Closed | 2023-08-24 | 2023-10-08 | 100% | 42156949 | External
10021 - SEC - PM022 | Project Firewall | PM022 | Closed | 2024-01-07 | 2024-01-09 | 100% | 69807032 | Internal
10022 - INV - PM015 | Liquidity Labyrinth | PM015 | OnGoing | 2023-03-18 | 2025-01-06 | 11% | 32952745 | External
10023 - INV - PM003 | Equity Elysium | PM003 | OnHold | 2023-09-08 | 2024-02-20 | 20% | 68503024 | Internal
10024 - SEC - PM006 | Security Shield | PM006 | Delayed | 2023-11-26 | 2024-01-24 | 46% | 91472239 | Internal
10025 - IMP - PM025 | Fiber Optic Frontier | PM025 | OnGoing | 2023-09-21 | 2025-10-20 | 49% | 19092780 | Internal
10026 - IMP - PM005 | Wireless Web | PM005 | Delayed | 2023-08-23 | 2023-11-08 | 81% | 1632114 | Internal
10027 - PRC - PM004 | ProcureTech Quest | PM004 | Delayed | 2023-03-20 | 2023-05-02 | 93% | 27705115 | External
10028 - INV - PM026 | Ascend Assets | PM026 | OnGoing | 2023-06-21 | 2026-11-25 | 15% | 83343310 | Internal
10029 - DSN - PM006 | Reimagine: Modernizing a legacy brand identity | PM006 | OnGoing | 2024-02-13 | 2024-07-05 | 71% | 95140524 | External
10030 - STG - PM008 | Strategic Nexus | PM008 | Closed | 2024-01-10 | 2024-01-30 | 100% | 80342528 | Internal
10031 - DSN - PM020 | Streamline: Improving user experience through design thinking | PM020 | Not Started | 2024-09-01 | 2025-05-30 | 0% | 67677123 | External
10032 - HRM - PM022 | Project Harmony | PM022 | OnHold | 2023-10-18 | 2025-03-14 | 3% | 85533796 | External
10033 - DSN - PM001 | Inclusivity: Designing for accessibility and diverse audiences | PM001 | OnGoing | 2024-01-06 | 2025-02-16 | 90% | 94106130 | Internl
10034 - INV - PM009 | Venture Vision | PM009 | Not Started | 2025-04-01 | 2025-09-15 | 0% | 27424707 | External
10035 - HRM - PM010 | People Connect | PM010 | OnGoing | 2023-03-22 | 2024-09-11 | 42% | 80374129 | External
10036 - IMP - PM020 | Project Backbone | PM020 | Not Started | 2024-06-15 | 2024-12-11 | 91% | 73214230 | External
10037 - PRC - PM002 | Sourcing Synergy | PM002 | Not Started | 2024-06-22 | 2024-10-15 | 96% | 66698637 | External
10038 - STG - PM004 | Quantum Leap | PM004 | OnGoing | 2024-01-16 | 2024-07-15 | 46% | 15386458 | Internal
10039 - PLN - PM020 | Project Roadmap | PM020 | Not Started | 2024-11-17 | 2025-07-20 | 70% | 29208332 | Internal
10040 - PRC - PM029 | Project Vendor Voyage | PM029 | Closed | 2023-08-10 | 2023-10-09 | 100% | 72471395 | Internal
10041 - PRC - PM009 | Supply Chain Serenity | PM009 | Closed | 2023-08-27 | 2023-12-05 | 100% | 95475182 | External
10042 - DSN - PM005 | Sustainability: Implementing eco-friendly design practices | PM005 | Not Started | 2024-08-01 | 2024-11-07 | 0% | 18138181 | Internl
10043 - PLN - PM022 | Planning Pioneers | PM022 | Not Started | 2024-07-15 | 2025-04-14 | 49% | 28802758 | Internal
10044 - PRC - PM020 | Procurement Pathfinders | PM020 | Not Started | No Plans | No Plans | 0% | 38222195 | External
10045 - PLN - PM018 | Project Forecast | PM018 | Delayed | 2023-05-02 | 2023-07-10 | 91% | 82568911 | Internal
10046 - DSN - PM012 | FutureVision: Design solutions for emerging technologies | PM012 | Delayed | 2023-09-05 | 2023-11-11 | 44% | 55235419 | Internl
10047 - HRM - PM025 | Workforce Wizards | PM025 | OnHold | 2023-11-06 | 2025-05-19 | 33% | 5255014 | Internal
10048 - DSN - PM026 | Storyteller: Crafting a compelling brand narrative | PM026 | Closed | 2023-12-08 | 2024-01-22 | 100% | 44474495 | External
10048 - DSN - PM026 | Storyteller: Crafting a compelling brand narrative | PM026 | Closed | 2023-12-08 | 2024-01-22 | 100% | 44474495 | External
10049 - FIN - PM009 | Project Cashflow | PM009 | Not Started | 2025-12-19 | 2026-05-18 | 55% | 80599632 | External
10050 - IMP - PM010 | Network Resilience | PM010 | Not Started | 2025-04-01 | 2025-10-02 | 0% | 30329066 | Internal
10051 - INV - PM003 | Fund Focus | PM003 | OnGoing | 2023-11-26 | 2025-07-10 | 44% | 62441560 | Internal
10052 - INV - PM021 | Invest Wise | PM021 | Delayed | 2023-01-08 | 2023-03-14 | 0% | 38941558 | Internal
10053 - PRC - PM003 | Project Cost Control | PM003 | Delayed | 2023-07-14 | 2023-08-14 | 49% | 39794998 | External
10054 - HRM - PM028 | Corporate Resilience | PM028 | Not Started | 2024-12-01 | 2025-08-10 | 0% | 51550937 | External
10055 - HRM - PM010 | HR Innovators | PM010 | OnGoing | 2023-04-01 | 2025-04-20 | 95% | 36949138 | Internal
10056 - DSN - PM003 | Empathy Engine: Fostering user empathy through design research | PM003 | Delayed | 2023-08-02 | 2023-10-21 | 59% | 49207142 | Internal
10057 - HRM - PM001 | Project Empowerment | PM001 | Delayed | 2023-05-06 | 2023-06-15 | 32% | 48851678 | External
10058 - DSN - PM004 | Cohesion: Integrating design across different platforms and channels | PM004 | Closed | 2023-03-19 | 2023-06-17 | 100% | 86589770 | External
10059 - SEC - PM015 | Threat Matrix | PM015 | Not Started | 2024-08-01 | 2025-04-16 | 0% | 36377345 | Internal
10060 - SEC - PM030 | Project Vigilance | PM030 | Not Started | 2025-05-01 | 2025-06-24 | 0% | 63099548 | External
10061 - PRC - PM007 | Vendor Vortex | PM007 | Closed | 2023-12-27 | 2024-02-10 | 100% | 39558198 | Internal
10062 - SEC - PM009 | SecureNet | PM009 | Not Started | 2024-10-01 | 2025-02-16 | 0% | 38050321 | Internal
10063 - PLN - PM016 | Planetary Ventures | PM016 | Closed | 2023-03-11 | 2023-06-19 | 100% | 82309459 | External
10064 - STG - PM025 | Vision Quest | PM025 | OnGoing | 2023-07-09 | 2025-01-07 | 19% | 61796553 | Internal
10065 - SEC - PM018 | Project Cipher | PM018 | OnGoing | 2023-04-08 | 2026-07-31 | 35% | 62234764 | External
10066 - IMP - PM025 | Cloud Connectivity | PM025 | Closed | 2023-04-08 | 2023-05-23 | 100% | 29654378 | External
10067 - PLN - PM029 | Project Synchrony | PM029 | Not Started | 2024-10-08 | 2025-08-04 | 18% | 34459741 | Internal
10068 - PLN - PM010 | Planning Horizon | PM010 | Delayed | 2023-05-08 | 2023-07-25 | 82% | 58825631 | External
10069 - PRC - PM023 | Procurement Excellence | PM023 | Closed | 2023-11-21 | 2024-01-05 | 100% | 16786801 | Internal
10070 - INV - PM017 | Alpha Finance | PM017 | OnGoing | 2023-03-18 | 2026-04-05 | 31% | 78471513 | External
10071 - INV - PM021 | Counting Countess | PM021 | Not Started | 2025-02-25 | 2026-08-10 | 90% | 90539022 | External
10072 - DSN - PM028 | Spark: Igniting creativity and innovation through design challenges | PM028 | Delayed | 2023-07-20 | 2023-09-04 | 35% | 53162941 | Internal
10073 - IMP - PM010 | Project Spectrum | PM010 | Not Started | 2025-04-01 | 2025-05-25 | 0% | 90408638 | Internal
10074 - DSN - PM023 | Eye-Catcher: Developing a captivating visual identity | PM023 | Not Started | 2025-04-01 | 2025-06-17 | 0% | 89690724 | External
10075 - FIN - PM025 | Budget Blueprint | PM025 | Delayed | 2023-05-04 | 2023-06-04 | 23% | 10600039 | Internal
10076 - HRM - PM028 | Talent Acquisition Quest | PM028 | Delayed | 2023-11-07 | 2023-12-15 | 83% | 73140957 | External
10077 - PLN - PM002 | Projects Insight | PM002 | Closed | 2023-08-18 | 2023-10-17 | 100% | 31806281 | External
10078 - PLN - PM014 | Planisphere | PM014 | OnGoing | 2024-01-05 | 2026-02-10 | 53% | 85077674 | External
10079 - DSN - PM006 | Infographics Unleashed: Creating impactful data visualizations | PM006 | Not Started | 2024-10-01 | 2025-03-05 | 0% | 74356257 | Internal
10080 - PRC - PM001 | Project Supplier Nexus | PM001 | Delayed | 2023-09-27 | 2023-11-16 | 73% | 51958523 | External
10081 - HRM - PM025 | Project Compass | PM025 | Closed | 2023-03-01 | 2023-04-15 | 100% | 81027698 | Internal
10082 - STG - PM025 | Project Pathfinder | PM025 | Closed | 2024-01-09 | 2024-01-18 | 100% | 99525335 | Internal
10083 - FIN - PM027 | Risk Navigator | PM027 | Not Started | 2025-10-12 | 2026-09-15 | 87% | 13101253 | Internal
10084 - SEC - PM027 | Guardian Force | PM027 | OnHold | 2023-08-06 | 2024-12-19 | 76% | 12320901 | Internal
10085 - PRC - PM013 | Strategic Sourcing Sprint | PM013 | OnGoing | 2023-04-27 | 2026-11-26 | 80% | 33159764 | External
10086 - PLN - PM017 | Project Orchestrator | PM017 | Closed | 2023-03-17 | 2023-06-25 | 100% | 91479261 | Internal
10087 - STG - PM010 | Stratagem Shift | PM010 | Not Started | 2024-10-01 | 2025-03-06 | 0% | 27006262 | Internal
10088 - PRC - PM009 | Procurement Innovators | PM009 | Not Started | 2025-08-01 | 2026-04-15 | 0% | 6102397 | Internal
10089 - IMP - PM010 | Router Renaissance | PM010 | Not Started | 2024-10-01 | 2025-03-22 | 0% | 43154127 | Internal
10090 - IMP - PM008 | Network Security Shield | PM008 | Closed | 2023-03-20 | 2023-06-18 | 100% | 66471582 | Internal
10091 - FIN - PM029 | Fiscal Fusion | PM029 | Closed | 2023-11-16 | 2023-12-31 | 100% | 87941887 | External
10092 - FIN - PM013 | Investment Nexus 2 | PM013 | Delayed | 2023-11-07 | 2023-11-24 | 86% | 47587368 | External
10093 - HRM - PM027 | Employee Experience Revamp | PM027 | Delayed | 2023-01-18 | 2023-02-14 | 87% | 16727826 | Internal
10094 - PRC - PM008 | Project ProcureNet | PM008 | OnGoing | 2023-11-05 | 2024-09-04 | 94% | 41246674 | Internal
10095 - PRC - PM012 | Supplier Spotlight | PM012 | Closed | 2023-08-20 | 2023-10-24 | 100% | 43778919 | External
10096 - IMP - PM022 | Project Latency Buster | PM022 | Not Started | 2025-04-01 | 2025-07-15 | 0% | 63928453 | Internal
10097 - STG - PM002 | Project Pinnacle | PM002 | Delayed | 2023-01-16 | 2023-03-21 | 9% | 69495540 | Internal
10098 - DSN - PM004 | Type Lab: Experimenting with typography for branding | PM004 | Closed | 2023-12-13 | 2024-01-27 | 100% | 54097725 | External
10099 - DSN - PM008 | Illustration Remix: Reimagining brand imagery through illustration | PM008 | OnHold | 2023-11-16 | 2024-09-08 | 63% | 69939165 | Internal
10100 - IMP - PM009 | Switchgear Symphony | PM009 | OnHold | 2023-11-28 | 2025-03-06 | 99% | 9319819 | Internal
10101 - INV - PM025 | Red Ink Rangers | PM025 | Not Started | 2025-08-26 | 2026-05-11 | 30% | 73228168 | Internal
10102 - IMP - PM002 | Network Expansion Quest | PM002 | Delayed | 2023-02-22 | 2023-05-14 | 65% | 45541007 | External
10103 - PLN - PM012 | Planning Nexus | PM012 | Not Started | 2024-07-12 | 2025-01-10 | 36% | 30222937 | Internal
10104 - DSN - PM016 | Iconography Evolution: Creating a consistent icon system | PM016 | Not Started | 2024-05-01 | 2024-09-15 | 0% | 17777085 | Internal
10105 - HRM - PM027 | Project Balance | PM027 | Closed | 2023-01-21 | 2023-04-26 | 10% | 12482124 | Internal
10106 - HRM - PM006 | Diversity Dynamics | PM006 | Not Started | 2024-03-01 | 2024-11-28 | 0% | 73604873 | Internal
10107 - HRM - PM011 | Project Engagement | PM011 | OnGoing | 2023-10-05 | 2026-05-21 | 92% | 76957644 | Internal
10108 - STG - PM008 | Horizon Bound | PM008 | OnHold | 2023-03-21 | 2024-01-15 | 65% | 34233559 | Internal
10109 - FIN - PM012 | Profit Pulse | PM012 | Not Started | 2024-04-16 | 2025-11-18 | 86% | 16453248 | External
10110 - FIN - PM016 | Debt Dynamo 2 | PM016 | Closed | 2023-06-10 | 2023-09-08 | 100% | 39606523 | Internal
10111 - PLN - PM026 | Project Pathfinder2 | PM026 | Closed | 2023-01-22 | 2023-04-22 | 100% | 49954029 | Internal
10112 - DSN - PM019 | Packaging Revolution: Redesigning product packaging for impact | PM019 | Delayed | 2023-06-13 | 2023-07-08 | 8% | 45281660 | External
10113 - HRM - PM004 | Leadership Lab | PM004 | Not Started | 2024-06-22 | 2025-08-08 | 47% | 56293029 | External
10114 - HRM - PM017 | Project Talent Pipeline | PM017 | Delayed | 2023-04-22 | 2023-06-03 | 83% | 9334166 | External
10115 - INV - PM030 | Project Rocky | PM030 | Delayed | 2023-10-24 | 2024-01-18 | 72% | 46881925 | Internal
10116 - DSN - PM020 | Motion Magic: Incorporating animation into design projects | PM020 | Delayed | 2023-07-20 | 2023-10-11 | 81% | 3569734 | Internal
10117 - IMP - PM008 | Project Bandwidth Boost | PM008 | OnGoing | 2023-07-04 | 2024-02-20 | 20% | 13809527 | External
10118 - SEC - PM018 | Project Lockdown | PM018 | OnGoing | 2023-05-07 | 2024-08-05 | 16% | 46291164 | Internal
10119 - INV - PM017 | Investor Insight | PM017 | Delayed | 2023-09-24 | 2023-10-11 | 71% | 92970758 | Internal
10120 - STG - PM029 | Project Catalyst | PM029 | OnGoing | 2023-08-23 | 2026-11-10 | 73% | 36799390 | Internal
10121 - STG - PM006 | Strategic Synergy | PM006 | Not Started | 2025-11-01 | 2026-06-27 | 0% | 56287183 | External
10122 - DSN - PM028 | Augmented Reality Experience: Designing for the AR world | PM028 | Not Started | 2024-08-01 | 2025-04-21 | 67% | 11264006 | Internal
10123 - PLN - PM029 | Planetary Alignment | PM029 | Closed | 2023-04-04 | 2023-06-03 | 100% | 77615856 | Internal
10124 - INV - PM001 | Capital Connect | PM001 | Closed | 2023-11-03 | 2024-02-11 | 100% | 44590179 | External
10125 - FIN - PM004 | Treasury Trailblazers | PM004 | OnGoing | 2023-07-05 | 2025-01-18 | 34% | 10037314 | Internal
10126 - STG - PM003 | Project Quantum2 | PM003 | Delayed | 2023-06-04 | 2023-08-20 | 5% | 96664429 | Internal
10127 - HRM - PM013 | Wellness Warriors | PM013 | Delayed | 2023-05-08 | 2023-06-18 | 27% | 91227940 | Internal
10128 - DSN - PM019 | Virtual Reality Voyage: Creating immersive VR experiences | PM019 | Not Started | 2024-07-01 | 2024-09-30 | 0% | 4377768 | External
10129 - PRC - PM030 | Procurement Efficiency Drive | PM030 | OnHold | 2023-02-15 | 2024-06-30 | 29% | 1826048 | Internal
10130 - DSN - PM024 | Design for Good: Using design to address social issues | PM024 | Not Started | 2025-03-28 | 2026-03-12 | 40% | 75613094 | External
10131 - PLN - PM004 | Project Visionary | PM004 | Not Started | 2024-10-01 | 2025-05-25 | 0% | 964575 | Internal
10132 - PLN - PM015 | Planning Compass | PM015 | Closed | 2023-01-24 | 2023-11-02 | 100% | 1614350 | External
10133 - SEC - PM008 | Security Ops | PM008 | OnGoing | 2023-04-17 | 2026-02-20 | 38% | 68169387 | Internal
10134 - SEC - PM025 | Project Safeguard | PM025 | OnHold | 2023-11-04 | 2025-04-28 | 38% | 16616806 | Internal
10135 - PRC - PM026 | Project ProcureWave | PM026 | Not Started | 2025-01-01 | 2025-08-27 | 0% | 85934947 | External
10136 - PLN - PM028 | Project Harmony2 | PM028 | OnGoing | 2023-07-14 | 2025-07-07 | 56% | 39578739 | Internal
10137 - SEC - PM009 | Sentinel Watch | PM009 | Delayed | 2023-09-17 | 2023-10-13 | 84% | 24230739 | Internal
10138 - INV - PM017 | VentureVortex | PM017 | Not Started | 2024-11-01 | 2025-05-27 | 0% | 49563762 | External
10139 - SEC - PM019 | Project CyberArmor | PM019 | Delayed | 2023-11-01 | 2023-12-02 | 27% | 70539902 | Internal
10140 - SEC - PM022 | Defender Initiative | PM022 | Not Started | 2025-04-03 | 2025-10-09 | 46% | 47182083 | External
10141 - SEC - PM017 | Project Risk Mitigation | PM017 | Not Started | 2024-11-01 | 2025-03-06 | 0% | 82224790 | External
10142 - PLN - PM014 | Planetary Optimization | PM014 | Delayed | 2023-12-07 | 2024-02-10 | 51% | 3831202 | External
10143 - SEC - PM017 | Security Nexus | PM017 | OnGoing | 2023-09-05 | 2025-06-12 | 16% | 39239681 | Internal
10144 - PLN - PM001 | Infra Resilience | PM001 | Not Started | 2025-08-01 | 2026-01-15 | 0% | 67167750 | Internal
10145 - IMP - PM014 | Firewall Fortitude | PM014 | Closed | 2023-07-02 | 2023-08-16 | 100% | 58029573 | External
10146 - INV - PM030 | Project Quantum | PM030 | OnGoing | 2023-12-24 | 2027-04-09 | 41% | 28697027 | External
10147 - STG - PM001 | Elevate Endeavors | PM001 | Closed | 2024-01-22 | 2024-02-01 | 100% | 94946222 | External
10148 - SEC - PM028 | Project Intrusion | PM028 | OnHold | 2023-09-03 | 2025-02-10 | 13% | 2580146 | External
10149 - PLN - PM029 | Planning Constellation | PM029 | OnGoing | 2023-02-25 | 2026-07-18 | 61% | 79038419 | External
10150 - STG - PM025 | Project Apex | PM025 | OnGoing | 2023-03-26 | 2025-10-06 | 49% | 620696 | Internal
10151 - IMP - PM001 | Network Optimization Odyssey | PM001 | Delayed | 2023-02-16 | 2023-05-16 | 34% | 49549726 | External
10152 - PLN - PM018 | Project Strategy | PM018 | OnHold | 2023-07-10 | 2024-01-06 | 41% | 59780712 | Internal
10153 - PLN - PM017 | Planetary Integration | PM017 | Not Started | 2025-08-01 | 2026-05-18 | 0% | 32902233 | External
10154 - PRC - PM030 | Vendor Value Quest | PM030 | Not Started | 2024-08-01 | 2025-05-13 | 0% | 33139545 | Internal
10155 - DSN - PM001 | Pixel Perfect: Redesigning a website for optimal user experience | PM001 | Not Started | 2024-03-28 | 2024-08-16 | 52% | 88753906 | External
10156 - HRM - PM024 | Project Succession | PM024 | Closed | 2023-07-02 | 2024-01-28 | 100% | 56468478 | External
10157 - HRM - PM007 | Inclusion Impact | PM007 | OnHold | 2023-07-14 | 2024-10-30 | 76% | 3855382 | External
10158 - STG - PM019 | Strategic Insight | PM019 | OnGoing | 2023-05-24 | 2026-11-18 | 57% | 48209823 | Internal
10159 - INV - PM003 | Investment Nexus | PM003 | Not Started | 2024-03-01 | 2024-10-16 | 0% | 60415727 | External
10160 - HRM - PM014 | Project Work-Life Harmony | PM014 | Closed | 2023-11-11 | 2023-12-26 | 100% | 35387210 | External
10161 - IMP - PM010 | Project Interconnect | PM010 | OnGoing | 2023-01-23 | 2024-02-23 | 22% | 96241002 | External
10162 - PRC - PM021 | Procurement Resilience | PM021 | Not Started | 2024-09-05 | 2025-09-21 | 3% | 56002805 | External
10163 - PLN - PM030 | Project Navigator | PM030 | OnGoing | 2023-08-24 | 2026-11-08 | 26% | 79905503 | External
10164 - PRC - PM013 | Project Supplier Symphony | PM013 | OnHold | 2023-10-01 | 2024-12-26 | 66% | 44499113 | Internal
10165 - IMP - PM017 | Cable Management Crusaders | PM017 | Not Started | 2025-05-01 | 2025-06-27 | 0% | 48234861 | Internal
10166 - SEC - PM022 | Cyber Resilience | PM022 | Not Started | 2025-05-01 | 2026-01-31 | 0% | 135161 | Internal
10167 - FIN - PM001 | Equity Endeavors | PM001 | Not Started | 2024-12-01 | 2025-03-30 | 0% | 44139276 | Internal
10168 - DSN - PM026 | Mobile Maestro: Optimizing app design for different devices | PM026 | Delayed | 2023-05-09 | 2023-06-27 | 38% | 63908240 | Internal
10169 - HRM - PM010 | Learning & Development Odyssey | PM010 | Delayed | 2023-01-12 | 2023-04-06 | 97% | 13742547 | External
10170 - DSN - PM003 | Microinteractions Matter: Adding delightful details to user interfaces | PM003 | Closed | 2023-08-26 | 2023-10-10 | 50% | 99662633 | External
10171 - STG - PM008 | Project Momentum | PM008 | OnGoing | 2023-12-07 | 2024-04-13 | 79% | 95610689 | Internal
10172 - PRC - PM015 | Cost Optimization Crusaders | PM015 | Not Started | 2025-03-23 | 2026-03-28 | 57% | 67407341 | External
10173 - SEC - PM029 | Project Access Control | PM029 | Closed | 2024-01-21 | 2024-02-06 | 100% | 50878322 | Internal
10174 - INV - PM015 | Project Wealth | PM015 | Delayed | 2023-10-02 | 2023-12-05 | 79% | 9651110 | Internal
10175 - PRC - PM026 | Procurement Agility | PM026 | OnHold | 2023-01-14 | 2024-08-04 | 9% | 30094452 | Internal
10176 - STG - PM024 | Project Ascend | PM024 | Delayed | 2023-06-01 | 2023-06-21 | 73% | 28741745 | External
10177 - HRM - PM005 | Project Retention Boost | PM005 | Not Started | 2024-05-01 | 2024-12-11 | 0% | 57065256 | Internal
10178 - PLN - PM011 | Planning Synergy | PM011 | OnGoing | 2023-03-24 | 2026-07-14 | 63% | 74573884 | External
10179 - SEC - PM004 | Security Fusion | PM004 | OnHold | 2023-11-14 | 2024-09-12 | 62% | 89138362 | Internal
10180 - PRC - PM016 | Project ProcureCraft | PM016 | Not Started | 2024-05-08 | 2024-09-12 | 90% | 17049977 | External
10181 - PLN - PM011 | Project Stellar 2 | PM011 | Closed | 2023-01-10 | 2023-04-10 | 100% | 55481387 | Internal
10182 - SEC - PM018 | Project Threat Intelligence | PM018 | Not Started | 2025-08-01 | 2026-04-26 | 0% | 58519771 | External
10183 - STG - PM008 | Strategic Resilience | PM008 | Not Started | 2024-03-26 | 2025-08-30 | 29% | 93966399 | External
10184 - PLN - PM002 | Planetary Synergy | PM002 | OnHold | 2023-05-20 | 2023-12-19 | 26% | 30691483 | External
10185 - STG - PM019 | Project Equinox | PM019 | Not Started | 2025-05-01 | 2026-01-22 | 0% | 98328705 | Internal
10186 - PLN - PM025 | Project Mastermind | PM025 | Closed | 2023-06-21 | 2023-09-29 | 100% | 72431716 | External
10187 - FIN - PM022 | Audit Aviators | PM022 | OnGoing | 2023-02-26 | 2025-08-04 | 86% | 1981438 | Internal
10188 - DSN - PM017 | Personalization Power: Implementing user personalization features | PM017 | Not Started | 2025-08-12 | 2026-06-16 | 28% | 83739961 | External
10189 - PRC - PM016 | Supplier Selection Saga | PM016 | OnHold | 2023-05-17 | 2024-04-05 | 78% | 40838791 | External
10190 - DSN - PM018 | Voice User Interface: Designing for voice-activated interactions | PM018 | Delayed | 2023-07-16 | 2023-08-12 | 70% | 22553488 | Internal
10191 - STG - PM003 | Project Genesis | PM003 | Delayed | 2023-08-18 | 2023-10-21 | 93% | 21419064 | Internal
10192 - FIN - PM029 | Tax Titans | PM029 | Closed | 2023-07-26 | 2023-09-09 | 100% | 97958429 | External
10193 - SEC - PM012 | Sentinel Alliance | PM012 | Not Started | 2025-02-27 | 2025-07-30 | 60% | 66993132 | External
10194 - DSN - PM017 | Gamification Guru: Using game mechanics to improve engagement | PM017 | Delayed | 2023-06-12 | 2023-07-08 | 53% | 20854118 | Internal
10195 - PRC - PM007 | Procurement Insight | PM007 | OnHold | 2023-03-25 | 2024-07-28 | 36% | 65040789 | External
10196 - IMP - PM012 | Network Traffic Tamer | PM012 | Closed | 2023-12-21 | 2024-02-04 | 100% | 24102225 | Internal
10197 - SEC - PM003 | Project Zero Trust | PM003 | OnGoing | 2023-03-21 | 2025-02-07 | 23% | 2476709 | External
10198 - DSN - PM010 | Accessibility Audit: Ensuring website and app accessibility | PM010 | OnHold | 2023-09-05 | 2025-02-27 | 18% | 82045363 | Internal
10199 - DSN - PM011 | A/B Testing Champion: Optimizing design through data-driven decisions | PM011 | Not Started | 2025-12-01 | 2026-05-28 | 0% | 1435381 | Internal
10200 - INV - PM011 | Project Horizon | PM011 | Not Started | 2025-01-20 | 2026-08-18 | 87% | 98947594 | External
10201 - SEC - PM010 | Security Compliance | PM010 | Closed | 2024-01-02 | 2024-01-21 | 100% | 37884493 | Internal
10202 - SEC - PM003 | Project Incident Response | PM003 | Not Started | 2025-09-01 | 2025-10-20 | 0% | 414137 | External
10203 - PRC - PM017 | Project Supplier Showcase | PM017 | OnHold | 2023-11-01 | 2025-05-30 | 13% | 20156023 | External
10204 - STG - PM004 | Strategic Pivot | PM004 | Not Started | 2025-12-21 | 2026-12-03 | 48% | 8777407 | Internal
10205 - SEC - PM004 | Cyber Guardians | PM004 | Not Started | 2025-02-06 | 2025-09-22 | 29% | 95300679 | External
10206 - HRM - PM030 | HR Analytics Expedition | PM030 | Delayed | 2023-04-26 | 2023-06-18 | 84% | 45405178 | Internal
10207 - DSN - PM008 | Progressive Web Apps Pioneer: Building PWAs for seamless user experience | PM008 | Not Started | 2024-08-02 | 2025-04-03 | 54% | 50541314 | External
10208 - FIN - PM017 | Financial Forecasters | PM017 | Closed | 2023-02-03 | 2023-05-14 | 60% | 25624251 | Internal
10209 - INV - PM021 | Risk Navigator 2 | PM021 | Delayed | 2023-05-14 | 2023-07-30 | 57% | 85208990 | Internal
10210 - SEC - PM002 | Project Secure Code | PM002 | OnGoing | 2023-12-08 | 2026-04-18 | 65% | 80648984 | Internal
10211 - IMP - PM021 | Project Data Pipeline | PM021 | Closed | 2023-11-07 | 2023-12-22 | 100% | 1606478 | Internal
10212 - HRM - PM021 | Project Performance Excellence | PM021 | OnGoing | 2024-02-01 | 2025-03-21 | 22% | 18557849 | Internal
10213 - INV - PM004 | Project Resilience | PM004 | Not Started | 2024-05-15 | 2025-01-02 | 24% | 35454877 | Internal
10214 - PRC - PM004 | Vendor Vitality | PM004 | Not Started | 2024-11-01 | 2025-06-18 | 0% | 76481041 | Internal
10215 - INV - PM019 | Debt Dynamo | PM019 | Not Started | 2024-03-01 | 2024-09-13 | 0% | 11979458 | External
10216 - PLN - PM009 | Planning Odyssey | PM009 | Closed | 2023-05-13 | 2023-06-27 | 100% | 34024198 | Internal
10217 - DSN - PM015 | Conversational Interface Creator: Designing chatbot interactions | PM015 | Not Started | 2025-11-24 | 2027-02-13 | 26% | 1365372 | External
10218 - PLN - PM013 | Project Sustain | PM013 | Closed | 2023-04-02 | 2023-07-01 | 100% | 46402390 | Internal
10219 - PRC - PM003 | Procurement Navigator | PM003 | OnGoing | 2023-12-17 | 2024-04-24 | 27% | 38232185 | External
10220 - DSN - PM004 | Fashion Forward: Sustainable fashion design project | PM004 | Not Started | 2024-06-01 | 2024-09-20 | 0% | 3583722 | Internal
10221 - SEC - PM014 | Security Audit Trail | PM014 | OnGoing | 2023-03-18 | 2025-07-28 | 37% | 78330404 | External
10222 - INV - PM025 | Project Treasury | PM025 | Closed | 2023-02-10 | 2023-05-11 | 100% | 66499305 | Internal
10223 - PRC - PM004 | Project ProcureLink | PM004 | Closed | 2023-05-27 | 2023-07-11 | 100% | 8894801 | Internal
10224 - SEC - PM008 | Project Data Encryption | PM008 | Closed | 2024-01-20 | 2024-01-22 | 100% | 68109260 | External
10225 - FIN - PM005 | Asset Alchemists | PM005 | OnGoing | 2023-06-07 | 2026-06-13 | 95% | 52273985 | Internal
10226 - FIN - PM015 | Cost Control Crusaders | PM015 | Not Started | 2024-02-21 | 2024-07-02 | 62% | 74790276 | External
10227 - SEC - PM025 | Threat Hunter | PM025 | Not Started | 2025-09-01 | 2026-03-24 | 0% | 29135698 | External
10228 - INV - PM020 | Portfolio Pioneers | PM020 | Not Started | 2024-10-22 | 2025-06-17 | 83% | 1477916 | External
10229 - DSN - PM028 | Interior Alchemy: Redesigning an office space for productivity | PM028 | Not Started | 2024-11-14 | 2026-03-17 | 98% | 80042283 | External
10230 - INV - PM021 | Project ROI | PM021 | OnGoing | 2024-01-16 | 2025-07-22 | 84% | 30206316 | Internal
10231 - STG - PM021 | Project Luminary | PM021 | Delayed | 2023-10-13 | 2023-11-12 | 63% | 70013041 | External
10232 - PLN - PM021 | Planetary Resilience | PM021 | Not Started | 2025-04-14 | 2026-04-03 | 83% | 36974159 | Internal
10233 - HRM - PM015 | Compensation Clarity | PM015 | Closed | 2023-08-20 | 2023-10-04 | 70% | 74130332 | External
10234 - HRM - PM009 | Project HR Transformation | PM009 | OnGoing | 2023-11-21 | 2026-12-21 | 5% | 38746146 | External
10235 - DSN - PM010 | Product Playground: Design thinking applied to product development | PM010 | Delayed | 2023-06-18 | 2023-08-27 | 97% | 9015058 | Internal
10236 - SEC - PM010 | Project Security Awareness | PM010 | Closed | 2024-01-19 | 2024-01-26 | 100% | 47712326 | External
10237 - SEC - PM006 | Security Patchwork | PM006 | OnHold | 2023-12-17 | 2025-02-02 | 8% | 40236338 | External
10238 - PRC - PM016 | Supplier Sustainability | PM016 | Delayed | 2023-01-23 | 2024-02-11 | 51% | 82291005 | External
10239 - IMP - PM006 | Protocol Pioneers | PM006 | OnGoing | 2023-12-13 | 2024-08-28 | 90% | 71563072 | Internal
10240 - PRC - PM016 | Procurement Nexus | PM016 | Closed | 2023-09-22 | 2023-12-31 | 100% | 60214700 | External
10241 - INV - PM011 | Project Valuation | PM011 | OnGoing | 2023-08-26 | 2024-12-18 | 19% | 65657301 | External
10242 - PRC - PM022 | Project ProcureFlow | PM022 | Not Started | 2025-03-01 | 2025-06-24 | 0% | 44535873 | External
10243 - STG - PM011 | Project Nexus | PM011 | OnGoing | 2023-06-21 | 2025-10-18 | 40% | 53620311 | Internal
10244 - HRM - PM023 | Career Development Quest | PM023 | Closed | 2023-07-26 | 2023-09-09 | 100% | 6668551 | External
10245 - PLN - PM016 | Insight Analyzer | PM016 | Closed | 2023-06-19 | 2023-09-27 | 100% | 58260766 | Internal
10246 - STG - PM016 | Strategic Edge | PM016 | Not Started | 2025-12-01 | 2026-03-29 | 0% | 17703057 | Internal
10247 - DSN - PM026 | Sustainable Packaging Pioneer: Eco-friendly packaging solutions | PM026 | Closed | 2023-02-27 | 2023-06-07 | 100% | 32676132 | Internal
10248 - HRM - PM012 | Project Workplace Wellness | PM012 | OnGoing | 2023-10-28 | 2024-10-06 | 3% | 29601196 | External
10249 - FIN - PM029 | Revenue Rendezvous | PM029 | Not Started | 2024-08-01 | 2024-10-21 | 0% | 52967473 | External
10250 - DSN - PM019 | User Research Revolution: Conducting in-depth user research studies | PM019 | OnHold | 2023-08-01 | 2025-02-10 | 29% | 65966264 | External
10251 - PRC - PM012 | Vendor Visionaries | PM012 | Closed | 2024-01-16 | 2024-01-18 | 100% | 19834536 | Internal
10252 - SEC - PM001 | Project Identity Management | PM001 | Closed | 2024-01-08 | 2024-01-24 | 100% | 2383153 | Internal
10253 - STG - PM006 | Project Phoenix | PM006 | Not Started | 2025-09-04 | 2027-03-11 | 38% | 98127144 | External
10254 - FIN - PM019 | Financial Frontier | PM019 | Not Started | 2025-09-01 | 2025-10-26 | 0% | 59095165 | Internal
10255 - SEC - PM010 | Cyber Watchtower | PM010 | OnHold | 2023-07-19 | 2024-04-10 | 50% | 64226227 | External
10256 - FIN - PM022 | Cash Management Mavericks | PM022 | Delayed | 2023-03-08 | 2023-06-05 | 80% | 39837510 | Internal
10257 - SEC - PM013 | Project Security Analytics | PM013 | Delayed | 2023-11-09 | 2024-02-05 | 47% | 45365106 | External
10258 - STG - PM013 | Project Uplift | PM013 | Not Started | 2024-05-01 | 2024-06-19 | 0% | 46049071 | External
10259 - FIN - PM023 | Financial Analytics Explorers | PM023 | Closed | 2023-08-01 | 2023-11-09 | 100% | 24708409 | Internal
10260 - INV - PM025 | Project Dividends | PM025 | Delayed | 2023-06-18 | 2023-07-19 | 83% | 86691422 | Internal
10261 - DSN - PM006 | Design Sprint Dynamo: Implementing design sprints for rapid prototyping | PM006 | OnGoing | 2024-01-04 | 2025-05-01 | 17% | 77599759 | External
10262 - PRC - PM027 | Procurement Harmony | PM027 | Delayed | 2023-08-25 | 2023-11-13 | 74% | 38620319 | External
10263 - STG - PM005 | Strategic Horizon | PM005 | Not Started | 2024-08-01 | 2025-01-18 | 0% | 45712106 | External
10264 - STG - PM027 | Project Zenith | PM027 | Closed | 2024-01-06 | 2024-01-21 | 100% | 41995829 | Internal
10265 - IMP - PM027 | Network Segmentation Strategy | PM027 | Delayed | 2023-01-11 | 2023-02-03 | 0% | 7763483 | Internal
10266 - HRM - PM009 | HR Compliance Crusaders | PM009 | Closed | 2023-11-07 | 2024-02-05 | 100% | 46577497 | External
10267 - DSN - PM019 | Brand Storytelling Studio: Crafting brand stories through various media | PM019 | Not Started | 2024-12-01 | 2025-08-05 | 0% | 80601833 | Internal
10268 - IMP - PM020 | Project WAN Wonderland | PM020 | OnHold | 2023-02-16 | 2023-06-10 | 83% | 56312784 | External
10269 - INV - PM021 | Project Bull Market | PM021 | Not Started | 2024-05-01 | 2025-01-18 | 0% | 37607586 | External
10270 - FIN - PM001 | Portfolio Pioneers2 | PM001 | Delayed | 2023-05-21 | 2024-01-29 | 7% | 77191357 | Internal
10271 - STG - PM009 | Project Empower | PM009 | Not Started | 2024-03-18 | 2025-02-14 | 97% | 7480763 | Internal
10272 - STG - PM010 | Strategic Compass | PM010 | OnGoing | 2023-06-18 | 2024-09-19 | 1% | 5148038 | Internal
10273 - PLN - PM017 | Planning Quest | PM017 | Not Started | 2024-06-01 | 2025-03-18 | 0% | 40898711 | External
10274 - PRC - PM029 | Project Supplier Success | PM029 | Delayed | 2023-08-12 | 2023-10-05 | 99% | 41663056 | External
10275 - STG - PM027 | Project Infinity | PM027 | Not Started | 2024-02-20 | 2025-06-21 | 3% | 75625933 | External
10276 - SEC - PM029 | Security Locksmiths | PM029 | Delayed | 2023-04-08 | 2023-06-11 | 98% | 17299018 | Internal
10277 - DSN - PM013 | Design Education Advocate: Promoting design education initiatives | PM013 | Not Started | 2024-05-01 | 2024-11-11 | 0% | 15506825 | Internal
10278 - HRM - PM003 | Project Talent Spotlight | PM003 | OnGoing | 2023-12-15 | 2027-06-10 | 24% | 56935794 | Internal
10279 - FIN - PM030 | Financial Wellness Warriors | PM030 | Not Started | 2025-06-01 | 2025-12-02 | 0% | 48578835 | External
10280 - PRC - PM024 | Cost Containment Quest | PM024 | OnHold | 2023-05-23 | 2025-01-11 | 62% | 60449287 | External
10281 - HRM - PM026 | Conflict Resolution Journey | PM026 | Not Started | 2024-07-04 | 2024-11-20 | 5% | 38376669 | Internal
10282 - FIN - PM019 | Capital Optimization Crew | PM019 | OnGoing | 2023-05-13 | 2025-07-18 | 95% | 38814209 | Internal
10283 - FIN - PM016 | Financial Compliance Commandos | PM016 | OnGoing | 2024-01-21 | 2025-12-21 | 48% | 11084253 | External
10284 - PRC - PM017 | Procurement Trailblazers | PM017 | OnHold | 2023-12-01 | 2024-08-20 | 92% | 76767290 | Internal
10285 - STG - PM003 | Project Quantum Leap | PM003 | OnGoing | 2023-04-13 | 2025-09-13 | 78% | 22322185 | External
10286 - FIN - PM021 | Financial Strategy Sages | PM021 | Delayed | 2023-11-15 | 2024-01-29 | 64% | 74808700 | External
10287 - INV - PM025 | Project Cat Market | PM025 | Not Started | 2025-04-19 | 2025-07-22 | 5% | 77058848 | Internal
10288 - HRM - PM022 | Project HR Agility | PM022 | Closed | 2023-08-09 | 2023-10-08 | 100% | 97116388 | External
10289 - INV - PM015 | Project Blue Chip | PM015 | Closed | 2023-08-12 | 2023-11-20 | 100% | 20069941 | Internal
10290 - HRM - PM026 | Leadership Development Voyage | PM026 | Closed | 2023-12-10 | 2024-01-24 | 100% | 21887592 | External
10291 - STG - PM014 | Strategic Vision | PM014 | OnGoing | 2023-05-15 | 2025-02-16 | 39% | 79600922 | External
10292 - STG - PM001 | Project Renaissance | PM001 | Delayed | 2023-10-08 | 2023-12-13 | 12% | 23800186 | External
10293 - PRC - PM030 | Project ProcureQuest | PM030 | Not Started | 2025-12-15 | 2026-08-11 | 54% | 98544709 | Internal
10294 - DSN - PM020 | Design Thinking for Social Impact: Applying design thinking to solve social issues | PM020 | OnGoing | 2023-07-13 | 2025-01-11 | 72% | 95968813 | External
10295 - SEC - PM008 | Project Biometric Authentication | PM008 | Delayed | 2023-10-21 | 2023-12-26 | 94% | 96441589 | Internal
10296 - DSN - PM007 | Design Futures Visionary: Exploring the future of design and its impact | PM007 | Not Started | 2025-10-01 | 2025-12-02 | 0% | 7351975 | External
10297 - HRM - PM013 | Project HR Synergy | PM013 | OnGoing | 2023-11-08 | 2026-06-11 | 15% | 52069411 | External
10298 - SEC - PM016 | Project Security Orchestration | PM016 | Closed | 2024-01-03 | 2024-01-15 | 100% | 67778124 | External
10299 - STG - PM004 | Coverage Finder | PM004 | OnGoing | 2023-11-12 | 2026-10-18 | 17% | 32216442 | Internal