## Slide 1
One Page GANTT Chart
Use this tool to present your project plan to leaders, stakeholders and your project team. Every time you present your project status, this format can be used as an update to the baseline created when you developed the original plan.
Projects are in constant flux and the original plan will often change as the team learns to manage risk, problem solve and flex their project outputs to meet evolving customer and leadership expectations.

## Slide 2: Project Name
Milestones | Start Date | End Date | Owner | Nov | Dec | Jan | Feb | Mar | Apr | May
Milestone 1 |  |  |  |  |  |  |  |  |  | 
Milestone 2 |  |  |  |  |  |  |  |  |  | 
Milestone 3 |  |  |  |  |  |  |  |  |  | 
Milestone 4 |  |  |  |  |  |  |  |  |  | 
Milestone 5 |  |  |  |  |  |  |  |  |  | 
Complete
In Progress
Planned
Behind
Risk
30/60/90-day review Project plan

## Slide 3: Launch Project Management Course Cohort 2
Milestones | Start Date | End Date | Owner | Jan | Feb | Mar | Apr | May
Confirm Program Design and Communicate | 1/6/2022 | 1/19/2022 | Susan |  |  |  |  | 
Determine Cohort two participants | 1/17/2022 | 2/4/2022 | Susan |  |  |  |  | 
Apply Continuous Improvement Techniques from previous Cohort | 1/17/2022 | 2/7/2022 | Susan |  |  |  |  | 
Refine Training Curriculum | 1/17/2022 | 2/4/2022 | Susan |  |  |  |  | 
Develop On-line Learning Management System with Content | 1/3/2022 | 6/19/2022 | Susan |  |  |  |  | 
Deliver Program | 2/14/2022 | 4/16/2022 | Susan |  |  |  |  | 
Final Presentation from Cohort | 4/19/2022 | 5/1/2022 | Jim |  |  |  |  | 
Perform Postmortem and implement Continuous Improvement | 5/2/2022 | 5/30/2022 | Susan |  |  |  |  | 
Complete
In Progress
Planned
Behind
Risk
30/60/90-day review Project plan