## CS6.1 Stakeholder PI
6.1 | Stakeholder Influence v Interest Grid
Ref | Stakeholder | Position | Organisation | Influence | Interest | Approach
S1 | Dany T | Chairperson & Shareholder #1 | ChefatHome
S2 | Jon S | CEO | ChefatHome
S3 | Robert B | Chief Marketing Officer | ChefatHome
S4 | Cecille L | Chief Operating Officer | ChefatHome
S6 | Jaime L | Manager Marketing | ChefatHome
S7 | Tyrone L | Manager Strategy | ChefatHome
EA1 | Missa | EA to Chairperson | ChefatHome
Sh1 | Shareholders | Shareholders | ChefatHome
Sh2 | Sansa S | Shareholder #2 | ChefatHome
Sh3 | Li, How, Fook | Board Members | ChefatHome
St1 | CAH Staff | Employees | ChefatHome
Cus1 | CAH Customers | Customers | ChefatHome
Law1 | Karl P | CEO | Pratt & Pratt
Law2 | Yara G | Senior lawyer - Mergers & Acquisitions | Pratt & Pratt
Reg1 | Stan B | Lead Regulator M&A | ASIC
Reg2 | Davos S | Principle Consultant | ASIC
Bid1 | Arya S | Chairman | ChefsRUs
Bid2 | Ned S | CEO | ChefsRUs
Bid3 | Melissa A | Legal Counsel | ChefsRUs

## CS6.1a Stakeholder PI
6.1 | Stakeholder Influence v Interest Grid
Ref | Stakeholder | Position | Organisation | Influence | Interest | Approach
S1 | Dany T | Chairperson & Shareholder #1 | ChefatHome | High | High | Manage Closely
S2 | Jon S | CEO | ChefatHome | High | High | Manage Closely
S3 | Robert B | General Counsel | ChefatHome | High | High | Manage Closely
S4 | Cecille L | Chief Operating Officer | ChefatHome | High | High | Manage Closely
S6 | Jaime L | Manager Marketing | ChefatHome | Medium | Medium | Keep Satisfied
S7 | Tyrone L | Manager Strategy | ChefatHome | Medium | Medium | Keep Satisfied
EA1 | Missa | EA to Chairperson | ChefatHome | Low | High | Keep Informed
Sh1 | Shareholders | Shareholders | ChefatHome | High | High | Manage Closely
Sh2 | Sansa S | Shareholder #2 | ChefatHome | High | High | Manage Closely
Sh3 | Li, How, Fook | Board Members | ChefatHome | High | High | Manage Closely
St1 | CAH Staff | Employees | ChefatHome | Low | High | Keep Informed
Cus1 | CAH Customers | Customers | ChefatHome | Low | Medium | Keep Informed
Law1 | Karl P | CEO | Pratt & Pratt | Medium | High | Keep Satisfied
Law2 | Yara G | Senior lawyer - Mergers & Acquisitions | Pratt & Pratt | Medium | High | Keep Satisfied
Reg1 | Stan B | Lead Regulator M&A | ASIC | High | Medium | Keep Satisfied
Reg2 | Davos S | Principle Consultant | ASIC | High | Medium | Keep Satisfied
Bid1 | Arya S | Chairman | ChefsRUs | High | High
Bid2 | Ned S | CEO | ChefsRUs | High | High
Bid3 | Melissa A | Legal Counsel | ChefsRUs | Medium | High

## Data (hidden)
Power | Interest
High | High
Medium | Medium
Low | Low

## CS6.2 Takeover Risk Analysis
6.2 | Takeover Risk Analysis
ID | Method | Takeover Risk Description | Impact on Company | Likelihood | Impact | Severity | Recommended Defense Strategy for ChefatHome (CAH) | Stakeholders | Owner
R001 | Open Market | ICC attempts to take control of CAH by buying a majority of shares on the market | Loss of control of CAH | Medium | High | High | 1. Poison Pill strategy. CAH could issue preferred stocks at a price below the market. Existing CAH shareholders (including Dany) could buy additional shares at a large discount to win back the majority. 2. PR campaign with shareholders | CAH Board Major shareholders Generall shareholders ASIC | Dany Jon Jon Robert
R002 | Hostile Bid | ICC goes directly to CAH's shareholders with an offer to buy their shares at a significant premium | Loss of control of CAH | Medium | High | High | 1. Crown Jewels strategy. This makes it possible for the CAH board to sell their most valuable asset, it's distribution arm, to the retailer upon loss of control of CAH, then buy it back at a later date. 2. PR campaign with shareholders | CAH Board Major shareholders General Shareholders ASIC General Public | Dany Dany Jon Robert Jaime
R003 | Proxy Fight | ICC convinces CAH shareholders to assign them their voting rights so they can replace the Board | Loss of control of CAH | Low | High | Medium | 1. Golden Parachute strategy. Dany feels that if she really loses the vote of shareholders then she and her Board will go, as long as they receive a generous payout to exit. 2. PR campaign with shareholders | CAH Board Major shareholders Generall shareholders ASIC | Dany Dany Jon Robert

## CS6.2a Takeover Risk Analysis
6.2 | Takeover Risk Analysis
ID | Method | Takeover Risk Description | Impact on Company | Likelihood | Impact | Severity | Recommended Defense Strategy for ChefatHome (CAH) | Stakeholders | Owner
R001 | Open Market | ICC attempts to take control of CAH by buying a majority of shares on the market | Loss of control of CAH | Medium | High | High | 1. Poison Pill strategy. CAH could issue preferred stocks at a price below the market. Existing CAH shareholders (including Dany) could buy additional shares at a large discount to win back the majority. 2. PR campaign with shareholders | CAH Board Major shareholders Generall shareholders ASIC | Dany Jon Jon Robert
R002 | Hostile Bid | ICC goes directly to CAH's shareholders with an offer to buy their shares at a significant premium | Loss of control of CAH | Medium | High | High | 1. Crown Jewels strategy. This makes it possible for the CAH board to sell their most valuable asset, it's distribution arm, to the retailer upon loss of control of CAH, then buy it back at a later date. 2. PR campaign with shareholders | CAH Board Major shareholders General Shareholders ASIC General Public | Dany Dany Jon Robert Jaime
R003 | Proxy Fight | ICC convinces CAH shareholders to assign them their voting rights so they can replace the Board | Loss of control of CAH | Low | High | Medium | 1. Golden Parachute strategy. Dany feels that if she really loses the vote of shareholders then she and her Board will go, as long as they receive a generous payout to exit. 2. PR campaign with shareholders | CAH Board Major shareholders Generall shareholders ASIC | Dany Dany Jon Robert

## CS6.3 Stakeholder Comms
6.3 | Stakeholder Communications Plan
Ref | Stakeholder | Position | Organisation | Influence | Interest | Approach | Frequency | Method | Owner
S1 | Dany T | Chairperson & Shareholder #1 | ChefatHome | High | High | Manage Closely
S2 | Jon S | CEO | ChefatHome | High | High | Manage Closely
S3 | Robert B | General Counsel | ChefatHome | High | High | Manage Closely
S4 | Cecille L | Chief Operating Officer | ChefatHome | High | High | Manage Closely
S6 | Jaime L | Manager Marketing | ChefatHome | Medium | Medium | Keep Satisfied
S7 | Tyrone L | Manager Strategy | ChefatHome | Medium | Medium | Keep Satisfied
EA1 | Missa | EA to Chairperson | ChefatHome | Low | High | Keep Informed
Sh1 | Shareholders | Shareholders | ChefatHome | High | High | Manage Closely
Sh2 | Sansa S | Shareholder #2 | ChefatHome | High | High | Manage Closely
Sh3 | Li, How, Fook | Board Members | ChefatHome | High | High | Manage Closely
St1 | CAH Staff | Employees | ChefatHome | Low | High | Keep Informed
Cus1 | CAH Customers | Customers | ChefatHome | Low | Medium | Keep Informed
Law1 | Karl P | CEO | Pratt & Pratt | Medium | High | Keep Satisfied
Law2 | Yara G | Senior lawyer - Mergers & Acquisitions | Pratt & Pratt | Medium | High | Keep Satisfied
Reg1 | Stan B | Lead Regulator M&A | ASIC | High | Medium | Keep Satisfied
Reg2 | Davos S | Principle Consultant | ASIC | High | Medium | Keep Satisfied
Bid1 | Arya S | Chairman | ChefsRUs | High | High
Bid2 | Ned S | CEO | ChefsRUs | High | High
Bid3 | Melissa A | Legal Counsel | ChefsRUs | Medium | High

## CS6.3a Stakeholder Comms
6.1 | 6.3 | Stakeholder Communications Plan
Ref | Ref | Stakeholder | Position | Organisation | Influence | Interest | Approach | Frequency | Method | Owner
S1 | S1 | Dany T | Chairperson & Shareholder #1 | ChefatHome | High | High | Manage Closely | Daily | 1-0n-1 | Project Director
S2 | S2 | Jon S | CEO | ChefatHome | High | High | Manage Closely | Daily | Phone Call | Project Director
S3 | S3 | Robert B | General Counsel | ChefatHome | High | High | Manage Closely | Daily | Email | Project Director
S4 | S4 | Cecille L | Chief Operating Officer | ChefatHome | High | High | Manage Closely | Daily | Email | Project Director
S6 | S6 | Jaime L | Manager Marketing | ChefatHome | Medium | Medium | Keep Satisfied | Weekly | Report (Internal) | Project Coordinator
S7 | S7 | Tyrone L | Manager Strategy | ChefatHome | Medium | Medium | Keep Satisfied | Weekly | Report (Internal) | Project Coordinator
EA1 | EA1 | Missa | EA to Chairperson | ChefatHome | Low | High | Keep Informed | Daily | Email | Project Coordinator
Sh1 | Sh1 | Shareholders | Shareholders | ChefatHome | High | High | Manage Closely | Quarterly | Presentation | Jon
Sh2 | Sh2 | Sansa S | Shareholder #2 | ChefatHome | High | High | Manage Closely | Weekly | Email | Jon
Sh3 | Sh3 | Li, How, Fook | Board Members | ChefatHome | High | High | Manage Closely | Weekly | Email | Dany
| St1 | CAH Staff | Employees | ChefatHome | Low | High | Keep Informed | Monthly | Presentation | Jon
| Cus1 | CAH Customers | Customers | ChefatHome | Low | Medium | Keep Informed | Monthly | Newsletter | Jaime L
Law1 | Law1 | Karl P | CEO | Pratt & Pratt | Medium | High | Keep Satisfied | Weekly | Report (Internal) | Robert
Law2 | Law2 | Yara G | Senior lawyer - Mergers & Acquisitions | Pratt & Pratt | Medium | High | Keep Satisfied | Weekly | Report (Internal) | Robert
Reg1 | Reg1 | Stan B | Lead Regulator M&A | ASIC | High | Medium | Keep Satisfied | As required | Report (External) | Robert
Reg2 | Reg2 | Davos S | Principle Consultant | ASIC | High | Medium | Keep Satisfied | As required | Report (External) | Robert
Bid1 | Bid1 | Arya S | Chairman | ChefsRUs | High | High
Bid2 | Bid2 | Ned S | CEO | ChefsRUs | High | High
Bid3 | Bid3 | Melissa A | Legal Counsel | ChefsRUs | Medium | High

## CS6.4 Comms Calendar
6.4 | Communications Calendar
| Week Comm. | Monday | Tuesday | Wednesday | Thursday | Friday
2020-02-03
2020-02-10
2020-02-17
2020-02-24
2020-03-02
2020-03-09
2020-03-16
2020-03-23
2020-03-30
2020-04-06
2020-04-13
2020-04-20
2020-04-27
Formulas:
Week Comm. = [Week Comm., row above]+7

## CS6.4a Comms Calendar (2)
6.4 | Communications Calendar
| Week Comm. | Monday | Tuesday | Wednesday | Thursday | Friday
| 2020-02-03 |  |  | Shareholders Mtg (Jon) | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-02-10 | 9am Mgt meeting (All Exec) |  |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon) | 9am Board Meeting (Board)
| 2020-02-17 |  | 10am Town Hall (Jon) |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-02-24 |  |  | ASIC Report (Robert) Monthly Newsletter (Jaime) | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-03-02 |  |  |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-03-09 | 9am Mgt meeting (All Exec) |  |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon) | 9am Board Meeting (Board)
| 2020-03-16 |  | 10am Town Hall (Jon) |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-03-23 |  |  |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon) | ASIC Report (Robert) Monthly Newsletter (Jaime)
| 2020-03-30 |  |  |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-04-06 |  |  |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-04-13 | 9am Mgt meeting (All Exec) |  |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon) | 9am Board Meeting (Board)
| 2020-04-20 |  | 10am Town Hall (Jon) |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
| 2020-04-27 |  | ASIC Report (Robert) Monthly Newsletter (Jaime) |  | Weekly Internal Report Weekly Email Weekly slide pack (Jon)
Formulas:
Week Comm. = [Week Comm., row above]+7

## Data2 (hidden)
Frequency | Method | Owner
Hourly | 1-on-1 | Dany
Daily | Phone Call | Jon
Weekly | Email | Robert
Fortnightly | Report (Internal) | Project Director
Monthly | Report (External) | Project Coordinator
Quarterly | Presentation | CEO
As required | Newsletter | Jaime L