## Slide 1
Project Conception and Initiation
Project Definition and Planning
Project Execution and Control
Project Close

## Slide 2: Initiate the Project
Define the project at a high level and determine feasibility
Write a Business Case
Create a Project Charter
Identify stakeholders and assign responsibilities

## Slide 3: Create a Project Charter

## Slide 4: Project Charter Basics
A document that:
  Introduces the project
  Aligns everyone’s thinking
  Obtain approval to proceed
Not very detailed
Should be 5 pages or less

## Slide 5: Project Charter Sections
Background information
  Anything a person would need to know why the project is a good idea
Scope
  Describe high level details of the end result
  Ensure full understanding of the boundaries
Objectives
  Measurable goals that can validate the project’s success
Governance
  List all of the project team members, sponsor, and the project manager

## Slide 6: Project Charter Sections
Schedule
  Any key dates or milestone targets
Budget
  One time cost to execute the project
  Ongoing support costs
C.A.R.D.
  List the constraints, assumptions, risks, and dependencies

## Slide 7: Project Charter Creation
Meet with full project team
Facilitate the meeting to ask probing questions about each section
Communication should bring out different views on the project and the discussion will help them to align
Discussions increase chance of risks and assumptions being identified
Project Manager drafts the Project Charter and sends out for project team feedback.
After making necessary edits, Project Manager sends out final Project Charter

## Slide 8: Project Charter Activity #1
Create a project charter template based on the key sections discussed
  Background information
  Scope
  Objectives
  Governance
  Schedule
  Budget
  C.A.R.D.

## Slide 9: Project Charter Activity #2
Think about a future project at home
  Putting in that new window
  Creating a new budgeting spreadsheet
  Painting that room
  Developing that application
Document the project details in the project charter template you created
Extra points for those that can facilitate a meeting with the “project team” and probe for project details to complete charter

## Slide 10: Understanding the Business Objective

## Slide 11: Understanding the Business Objective
  What is the purpose of the project?
  What are the goals and objectives of this project?
  In the eyes of this project, what is success, and how will it be measured?

## Slide 12: Writing and Presenting a Business Case

## Slide 13: Business Case Basics
  What is a Business Case?
  Why is it used?
  When is it used?
  Who creates it?

## Slide 14: What is a Business Case?
A decision-making tool used to determine the effects a particular decision will have on profitability.

## Slide 15: Why is a Business Case Used?
Intended to convince key decision-makers of the merits of a particular course of action.

## Slide 16: When is a Business Case Used?
A business case is done on nearly every action, but not always in a written format.
The business case is created prior to the project being started. This frames up the return on investment prior to taking the action.

## Slide 17: Who Creates a Business Case?
A business case is generally created by a business executive, a business manager, or a business analyst.

## Slide 18: 5 Phases to an Effective Business Case
  Phase 1 - Initial Analysis
  Phase 2 – Determine Potential Solutions
  Phase 3 – Write the Business Case
  Phase 4 – Review Business Case
  Phase 5 – Present the Business Case

## Slide 19: Initial Analysis
Thoroughly understand the problem or opportunity
Determine high level requirements
Identify data needed to support the business case (ROI)
Validate with decision makers the high level return is worth the potential investment
Analyze likelihood project will be approved and if you should continue

## Slide 20: Determine Potential Solutions
Identify all possible solutions to the problem.
  Benefits
  Costs
  Timetable of project
  Time before a return on investment is realized
  Risks
*One of your solutions should be to do nothing

## Slide 21: Writing the Business Case
Executive Summary
Problem Statement
Analysis
Solution Options
Cost-Benefit Analysis
Recommendation

## Slide 22: Review Business Case
Validate problem statement justifies a call to action
Ensure all valid solutions are given
Double check cost-benefit analysis calculations
Objectively dissect your recommendation
Correct any spelling or grammatical mistakes
Ask another person to closely review the document
Get project buy-in of two key stakeholders

## Slide 23: Present the Business Case
Remind yourself, they haven’t seen this before
Clearly define the problem and business need to act
Give your recommendation
Explain the return on investment (ROI)
Touch on each risk, but unless asked, don’t dive in deep
Mention your stakeholder backers
Close the presentation summarizing the benefits and ROI